## Slide 1
Project reporting workflow (Draft)
Input from Benef & Partners
Instructions are sent
Final report assembled by SC
WP coordinators send detailed instructions (to Task Leaders and Facility Coordinators)
TLs and FCs assemble the requested material & submit it to the WPCs.
WP Coordinators assemble the WP Activity Report & submit it to the SC (consistency already checked for each WP)
SC assembles the P2 report and sends it to the PO
Report document sent to the GB chairperson for approval
Project office submits the report to the EC
4 May
28 Oct 2026
22 Oct
5 Oct
19 Sept
4 Sept
PO check and correct the report (formats, completeness, etc.); check the consistency of the data with financial data; send to the SC for approval
13 Oct
WP Activity Report
Project Office
GB chairperson approval
Final submission (deadline: 30 oct)
Requested information
provided from beneficiaries
Few things will happen in August, also for TNA.
We should stress the TLs and FCs to work on the report during June-July.
Meeting FINE could be a good time to discuss some draft parts
filling user data to the portal
Part B - narrative
Part A - tables
Publications, Communications and Dissemination Activities, Results, impact, critical risks
Researchers section (staff) updated by each partner
Project Summary
16 Oct
Financial statement completed by partners
Users’ data (final, complete and correct) uploaded on the repository
29/06-01/07 (FINE)
dedicated Final Reporting helpdesk for the report (Barbara, Marco, Chiara/ Sara, Stefania; WPCs if/when necessary)
Focus on final report