## Slide 1
Summary of IAPP scientific activities into 4 years
P. Giannetti
INFN of Pisa

## Slide 2
List of Work Packages & WP leaders
Prototype Construction & Production Validation (PRIELE, M1-M42)
Infrastructure & Integration (CAEN, M1-M48)
Commissioning (CERN, M12-M48)
Architecture Simulation (UniPisa, M1-M48)
Image Processing (UniPisa, M25-M48)
Silicon Detectors (CNRS,M1-M48)
Outreach (AUTH, M1-M48)
Workshops & Trainings (AUTH, M1-M48)

## Slide 3
Participation to Work Packages

## Slide 4
WP1: Prototype Construction & Production Validation
(Priele)
Objectives
Construction and standalone validation of an FTK processor based on
Serial Link technology for Level 1 and Level 2 trigger applications
Transfer of Knowledge to PRIELE for board assembly and validation
and among all research institutions about Associative Memory technology
Description of work
Now:
T.1.1. Installation of FTK test stand at PRIELE and AUTH for tests & ToK
T.1.2. Design of SLP2 PC boards (schematic capture, layout & routing)
T.1.3. Design of SLP2 firmware (HDLs language and use of Xilinx CAD)
Summer?
T.1.4. SLP2 PCB construction
August – September-October?
T.1.5. SLP2 assembly at PRIELE
T.1.6. Standalone validation of SLP2 at PRIELE before integration at CAEN
Greek tasks after ToK
T.1.7.-T.1.11. Same tasks for SLP1 as T1.2-T.1.6 for SLP2

## Slide 5
Deliverables
D.1.1. SLP2 prototype constructed at PRIELE – delivery date M12 (end 2013)
D.1.2. 1st FTK production assembled at PRIELE – delivery date M32 (2015)
D.1.3. SLP1 prototype constructed at PRIELE – delivery date M36 (end 2015)
D.1.4 . 2nd FTK production assembled at PRIELE – delivery date M42 (2016)
Milestones
M.1.1. SLP2 prototype validated at PRIELE - M12
M.1.2. FTK Technical Design Report: Atlas evaluation of prototypes - M12
M.1.3. 1st FTK production validated at PRIELE – M32
M.1.4. SLP1 prototype validated at PRIELE – M36
M.1.5. 2nd FTK production validated at PRIELE – M42
WP1: Prototype Construction & Production Validation

## Slide 6
WP1: Prototype Construction & Production Validation
Risk Analysis
M.1.1. Risk: SLP2 validation fails; not used in the FTK demonstrator.
Action: (a) demonstrator based on existing AMBFTK boards;
(b) SLP2 design will be fixed and a second prototype built.
M.1.2. Risk: Atlas review of entire FTK system fails. Action: continues R&D
to be used for longer-term goals (L1 applications for muons, for Phase II
LHC upgrade, and Image Processing); productions D.1.2 and D.1.4 dropped.
M.1.3. Risk: major fault found in produced boards. Action: investigate &solve
the problem, then repeat production. We will propose to ATLAS a later
commissioning to be approved by the experiment.
M.1.4. Risk: SLP1 validation fails; not used in the Atlas phase I upgrade.
Action: continue L1 R&D for a second prototype during the last year.
M.1.5. Risk: major fault in production due to factory responsibility. Action:
propose to ATLAS a later commissioning to be approved by the experiment.

## Slide 7
WP2: Infrastrucure & Integration (CAEN)
Objectives
Infrastructure construction and validation (racks, crates, power supplies, cooling)
Validation/integration of prototypes from Europe, Japan and USA
Software development for system test/control/monitoring
Transfer of Knowledge among CAEN and research institutions
Description of work
Now 2013:
T.2.1. Installation of a vertical slice (VS) at CAEN for board integration, validation tests & ToK
T.2.3. Software development for tests of the VS
T.2.4. Tests and validation of the baseline FTK system for the demonstrator
After:
T.2.2. Prototyping of a CAEN power supply for the final crate (5kW)
T.2.5. Tests and validation of the SLP2-based system
T.2.6. Tests and validation of the SLP1-based system
T.2.7. Tests of cooling and mechanics of a rack with complete final crates

## Slide 8
Deliverables
D.2.1. VS infrastructure at CAEN for FTK demonstrator integration – M6 (2013)
D.2.2. FTK demonstrator fully integrated with old power supply - M12 (end 2013)
D.2.3. CAEN power supply ready for integration - delivery date M18 2014
D.2.4 FTK cooling and mechanical tests completed - delivery date M20 2014
D.2.5. SLP2 fully integrated - delivery date M20
D.2.6 SLP1 fully integrated - delivery date M48
WP2: Infrastrucure & Integration (CAEN)

## Slide 9
WP2: Infrastrucure & Integration (CAEN)
Milestones
M.2.1. FTK demonstrator running flawlessly at CAEN – M12 January 2014
M.2.2. SLP2-based FTK running flawlessly at CAEN – M20
M.2.3. Infrastructure (crate, cooling, power supplies, mechanics) validated – M20
M.2.4. Comparison and choice between FTK baseline and SLP2 systems – M20
M.2.5. SLP1-based FTK running flawlessly – M48
Risk Analysis
M.2.1 Risk: problems detected in the FTK demonstrator. Action: Solve the problems and move
commissioning start at CERN to a later date (maximum delay allowed by contingency is 8 months).
M.2.2 Risk: problems detected in the SLP2-based FTK. Action: Choose baseline technology
M.2.5 Risk: major problems in the SLP1-based FTK. Action: This system is not suitable for ATLAS
Phase I

## Slide 10
WP3:Commissioning (CERN)
Objectives
Infrastructure installation and validation at point 1 (racks/crates/power supplies)
Board installation/validation and running control/functional monitoring
Transfer of Knowledge among CAEN and research institutions for board
Commissioning/maintenance
Description of work
T.3.1. Installation of Infrastructures, validation tests & ToK
T.3.2. Installation of boards (SLP2 or FTK baseline) for the demonstrator
T.3.3. Tests and validation of the FTK demonstrator
T.3.4. T.3.5 as T.3.2, T.3.3. for the first production
T.3.6. T.3.7. as T.3.2, T.3.3. for the second production
Deliverables
D.3.1. FTK demonstrator commissioned – delivery date M22 (end 2014)
D.3.2. FTK first production commissioned – delivery date M34 (end 2015)
D.3.3. FTK second production commissioned - delivery date M46

## Slide 11
Milestones
M.3.1. FTK demonstrator running flawlessly inside Atlas– M24 (end 2014)
M.3.2. FTK first production running flawlessly inside Atlas – M36 (end 2015)
M.3.3. FTK second production running flawlessly inside Atlas – M48 (end 2016)
Risk Analysis
M.3.1., M.3.2., M.3.3. Risk: any kind of failure at level of commissioning will produce the same
action: understand the problem and fix it, requiring extra time to Atlas for the final activation.
WP3:Commissioning (CERN)

## Slide 12
WP4: Simulation (University of Pisa)
Objectives
Production of test vectors to validate hardware configurations
Definition of Level 1/Level 2 architectures to optimize physics reach
Description of work
T.4.1. SW simulation of the HW details of the FTK demonstrator
T.4.2 Production of test vectors for the FTK demonstrator
T.4.3. Production of test vectors for the SLP2 based FTK
T.4.4. Study of high level event selection algorithms based on FTK tracks
T.4.5. Study of the L1 Muon Trigger architecture
T.4.6. Production of test vectors for the SLP1 based FTK
Deliverables and Milestones
D.4.1. - FTK Demonstrator detailed simulation - delivery date M9 October 2013
D.4.2. – Test Vectors for the FTK demonstrator - delivery date M10
D.4.3. - Test Vectors for the SLP2 based FTK - delivery date M16
D.4.4. - Trigger table for FTK demonstrator with performance prediction – delivery date M25
D.4.5. - SLP1 architecture simulation - delivery date M28
D.4.6. - SLP1 detailed simulation - delivery date M38
D.4.7. - Test Vectors for the SLP1 based FTK - delivery date M42
Is it compatible
With L1 muon
Trigger?

## Slide 13
WP4: Simulation (University of Pisa)
Milestones
M.4.1. FTK Demonstrator simulated in its general architecture – M6
M.4.2 Predicted trigger performances meet Atlas requirements – M26
M.4.3. Approval of SLP1 architecture in Atlas – M30
Risk Analysis
M.4.1. Risk: general simulation not ready. Action: increase manpower to satisfy test vector
deliveries.
M.4.2 Risk: predicted trigger performances do not meet Atlas requirements, FTK could be rejected. Action: FTK productions could be dropped, R&D program would continue
M.4.3. Risk: SLP1 architecture rejected by Atlas . Action: correct the architecture to satisfy Atlas requirements and propose the architecture for later Phase II Atlas upgrades.

## Slide 14
WP5: Image Processing (University of Pisa)
Objectives
Test Associative Memory capability to extract relevant features from
natural/medical images
Evaluate impact on medical imaging/diagnosis and robotic automation
Description of work
T.5.1. Installation of a separate crate and AM system at CAEN for image processing
T.5.2. Production of software and firmware for image formatting and system training
T.5.3. Evaluate performances of natural still image processing
T.5.4. Perform tests on moving image processing
T.5.5. Perform tests on medical image processing
Deliverables and Milestones
D.5.1. Infrastructure at CAEN for Image Processing – delivery date M26
D.5.2. Software & firmware ready for training and image processing - delivery date M30
D.5.3. Performances of natural still image processing - delivery date M34
D.5.4. Results of tests on movie processing - delivery date M40
D.5.5. Results of tests on medical image processing - delivery date M48

## Slide 15
Milestones
M.5.1. Hardware still-image processor running flawlessly – M34
M.5.2. Filtering and data reduction of natural movies running flawlessly – M40
M.5.3. Procurement of medical image data – M42
Risk Analysis
M.5.1. Risk: Hardware still-image processor not working as expected. Action: understand the problem and fix it, reducing the time available for users inside the project time window.
M.5.2. Risk: the movie processing is not producing the expected results. Action: try more to
understand problems and fix them, reducing the time available for medical image processing
M.5.3. Risk: we fail to procure medical image data. Action: drop this part of the program.
WP5: Image Processing (University of Pisa)

## Slide 16
WP6:Silicon Detectors (CNRS)
Objectives
Optimizationof CAEN power supply for LHC pixel detectors (phase-II)
Description of work
Now 2013:
T.6.1. Setup of a test bench for PS performance evaluation at CAEN
T.6.2 Measurements on PSes equipped with undamaged readout chips (FEI4 devices)
Next time 2015
T.6.3. Optimization of PSes with irradiated devices
T.6.4. Tests with optimized Pses
Deliverables and Milestones
D.6.1. Test bench – delivery date M12
D.6.2. Standard characterization – delivery date M24
D.6.3. Optimized power supplies and their characterization - delivery date M34
M.6.1. ATLAS review of CAEN power supplies – M32
Risk Analysis
M.6.1. Risk: Atlas is not interested to the proposed CAEN power supplies solution. Action: try to
change the solution to meet Atlas requirements.
To be done
In 2013!!