## Slide 1
Status of the Installation
Ferdinand Hahn

## Slide 2: KTAG
5/8 sectors equipped
DCS system in pogress
DAQ commissioning in progress
Test pressure scan this week (t.b.c)

## Slide 3: GTK
In the Pit:
  Finish beam sector 3+4 by end of this week.
  Vessels (1,2+3) are in place (alignment this week)
  Cooling system installation started (expected operational > 22/09).
Detector Assembly:
Test assembly with dummy detector successfully done
Bottlenecks: carrier board, assembly work, testing,…
Tight schedule!
Target: Install 2 detectors…. for the start of the Run
3 stations equipped as of November

## Slide 4: CHANTI
Detector installed
RO connection (feed-through Flanges missing) and test in September
Beam sector under vacuum
Commissioning in September

## Slide 5
LAV 12 Installation on 28.08.2014

## Slide 6: LAV
All 12 LAV’s are installed!
  Modifiactions of roller width (done by Frascati Team)
RO boards + TEL’s are being installed
Commissioning well advanced
DCS okay.
Congratulations to the Frascati/Pisa Team for the excellent work!

## Slide 7: Straw Tracker
Detector Installation
  STRAW 1-3 installed
  Straw 4 installation next week
  Cabling done except for Straw 4
RO being tested (using 1 SRB)
24/32 SRB’s available for the start of the Run
May be delayed again
Target:
Trigger-less RO at the beginning
Possibly: all SRB’s and triggered RO in November.

## Slide 8: RICH + Al Beam Pipe
Mirrors installed and aligned
Rear window closed
Suspension bar for beam pipe (installation ongoing)
Front window closure -> this week
Al- beam pipe installation in weeks 36+37.
Al Beam pipe Leak test (??)
RICH Cabling in in weeks 37+38
FE boards will be installed end September
RICH filling, perhaps, in first week of October
Schedule: tight, but do-able
Risk: RO commissioning time very short

## Slide 9: Beam Pipe Suspension

## Slide 10: SAV
SAC:
  Installed and aligned
  RO / Gandolf being prepared
IRC:
  Detector delivered
  Installation possibly in week 37

## Slide 13: LKR + LKR L0
LKR hardware okay
CREAM RO installed and operational.
LKR L0 trigger
  Hardware installation continous.

## Slide 14: MUV
MUV3
  Installation okay
  RO still problematic:
    New CFD board prototype could not be tested (problem with threshold DAC, intermittent contacts on the board,…)
    Decision was made to go back to old CFD‘s (like in 2012), requires a lot of tuning work, which needs to be done in September.
MUV2:
  Installation okay
  CREAM RO (on loan from LKR) been prepared / details to be worked out…
MUV1:
  Detector still in Mainz, status update in MUV WG
  We have to evaluate this week, what is realistically possible

## Slide 15: Status Vacuum System
Decay tube (Sector 5)
Vacuum instruments installation completed
Remote control of all instruments (apart cryopumps) ready
Pressure reached during Decay tube commissioning:
1.2E-6 mbar (decay area)
3.2 E-6 mbar (straw area)
Still water outgassing dominated.
No major leaks on system, neither on vacuum tank nore on Straw system.
Other sectors
Remote control of other sectors not yet ready (2 weeks necessary).
Sector 4: pumped and leak tested
Sector 1: being pumped
Sector 2: start pumping early next week
Sector 3: being being closed, pumping expected end of next week (week 36)
Sector 6 (LKr): switch to new pumping and control by week 37
Interlocks will be available by week 38
Berthold Jenninger

## Slide 16
7x Cryopumps and DN620 gate valves
Roughing line
Decay Tank
Vacuum gauges
5x Roughing valves
(DN25 and DN40)
Roughing pumping group
Turbo group
(DN250)
Synoptics of Decay tube vacuum control
Color code indicates present status (on, off, open, close, communication , under- or overrange ...)
Berthold Jenninger

## Slide 17
Details and history
Examples
Details on Turbo pumping group
Details on Cryo pumping group
History penning gauges when starting cryopumps
Instabilities in profibus network understood and resolved
Turbo pumping only
(one month)
Start cryopumping
Berthold Jenninger

## Slide 18
Residual gas spectrum shortly before venting
18
H2O
2
H2
28
N2
CO
C2H4
40
Ar
44
CO2
Only one cryopump connected
Expected ratio Ar/CO2: 0.15
Measured Ar/CO2: 0.6
(supposing same pumping speed for Ar and CO2,
i.e. only pumping on second stage of cryopump)
(probably first cryopump stage at 90 K contributes to CO2 pumping)
Berthold Jenninger

## Slide 19: Conclusions
Detector installation is getting to the end.
  Remaining attention areas:
    Al beam pipe + IRC
    RICH-Straw Link + Straw 4
    RICH RO
    GTK completion
    LKR L0 installation
    MUV3 CFD board tuning
    MUV1 installation
DAQ commissioning work
  Hardware deliveries drive the schedule