## Slide 1: TDAQ commissioning
R. Fantechi
2/09/2014

## Slide 2: Milestone table (7/2014)
Week 23/6: L0TP/Torino test (@Pisa): at least 2 primitive sources, writing to LTU, choke/error test
Week 7/7: full-speed writing test on PC farm at CERN: at least 4 TEL62 plus other systems (CREAM) and run control
Week 21/7: L0TP test (@CERN) with primitives from LKr/L0, MUV3, LAV, RICH and CHOD
Week 28/7: L0TP test with primitives from LKr/L0, 1 CREAM crate + 1 set of TEL62 + farm
(Salamon, De Simone, Venditti, Fantechi)
Week 28/7: XML configuration file test from run control to all subdetectors
Week 4/8: have the maximum possible hardware installed, with at least one complete readout chain from each sub-detector
Week 18/8: GPU test with simulated primitives from 2 RICH sources and local writing
Week 15/9: full-speed readout test with 10 MHz primitives from all L0 subdetectors and 1 MHz readout
Done
Pcfarm installed, tests done with CREAMs and 1 TEL62
Test with 2 TEL62, integration with run control
Then completed with CREAM readout, fake triggers
Integration of L0TP, Tdspy, LKR calib, LKR init
Not done, add few more TEL62, run with multiple destination PCs
See Lamanna’s talk
Start to setup various detectors, according to TEL62 arrival

## Slide 3: Activities during the last months
  PC farm
  Network
  L0TP
  LKr readout
  LKr trigger
  Run control
  Cabling, crates, etc

## Slide 4: PC farm
PC Farm installed
  30 dual 8-core machines
    Possibility to install one GPU each
    10 Gb links to the router for data input
    1 Gb links to the mergers
  2 new merger machines
    In addition to the existing one
    Output connected to the CDR
  Actually 21 machines configured and running
    Complete installation soon, move old machines as dev ones
  Cooling installation under completion

## Slide 5: PC farm – Software and CDR
Continuous exercising of the PC farm SW
  Mainly to test the CREAM system
    Several bugs found and fixed
    More tests needed to understand high rate capabilities
      Also with many more TEL62 running at full L0 speed
    Need of specific debug tools
CDR configuration
    Followed by Paolo Valente and Emanuele Leonardi
    2012 scripts upgraded with the help of Felice Pantaleo
    Setup of a run/burst bookkeeping facility

## Slide 6: Network
Router
  All the fibers from ECN3 connected
    Only missing the three connection to GTK (in the same room)
    1-2 ports left free
Switches
  Al switches ready with the basic configuration
  Specific configurations done
    Mirror ports for LKr and the last switches installed, to be extended to all
    Multicast capabilities for the LKr
Link with the CDR
    To be moved to 10 Gb (1st week of September)
Monitoring/performance studies
  Have a basic access to equipment counters/monitor tools to react quickly to failures or overhead
  Setup a channel with IT to study the performance of the network and optimize it for high rates

## Slide 7: Trigger processor
“Torino” flavor installed in July
  Based on Altera DE4 evaluation board + custom board for TTC, choke/error, LTU interface
  First version of the firmware tested successfully
    With primitives loaded from a file inside 2 TEL62s
    With primitives generated by the primitive generator of LAV firmware
  Periodic triggers implemented in August
  Run control integration completed
Switch to/from TALK L0tp is only moving a cable
  i.e. For LKr calibrations

## Slide 8: LKr readout
  CREAM installation almost completed
    28 crates installed, all with VME bridge and TTC module
    430 modules out of 432 are installed
    27 crates fully cabled
    Choke/error boards installed, not yet fully tested
    Currently 22 crates readout, the rest partially used to test the TELDES boards
    Some problems at the beginning with high humidity in the barrack: water on the heat exchangers
      Deumidifier installed and running continuously
      Temperature, humidity and dew point continuously monitored, alarms sent to various people

## Slide 9: LKr trigger
TELDES tests
  Continuous tests of 4 TELDES boards connected to CREAMs to validate cables
  Some problems due to the installation of the test TEL62 in a spare crate with high ripple on 3.3 V (need check)
  To be validated fully in the final crates
Cabling
  First installation round with 3 racks
  Problems understood
    Clean and nice
  Two and half more weeks needed

## Slide 10: Run Control
Integration tests done by Nicolas
  Mainly for the new interface with xml conf files
  LTU initialization OK
  LKr Calibration initializer and cycling ok
  Prototype of CREAM initializer ok
  This will be cloned by the STRAW
  L0TP interface OK
  New version of TDSPY tested
  Work going on the PC Farm interface
To be completed in the next weeks

## Slide 11: Infrastructure
Crates
  All crates now at CERN
    Include a couple of additional spare power supplies
TEL62/TDCB
  8 TEL62 arrived 14/08, some distribution done
  30 in Pisa first week of September
    Define the policy for distribution
  50 TDCB arrived 14/08, more to come
Cabling
  Ethernet cabling for RICH05 (saleve side) done
Choke/error
  All CHEF boards available (LKr ones already installed)
    Need little mods

## Slide 12: Software EOB data
Need to add information coming from non-TEL62 based detectors
  i.e. DCS data for the KTAG, LKr calibration settings, Straw eob data, etc.
Basic mechanism discussed, protoype implemented, to be reviewed
  Based on DIM publishing
  Add the data to the EOB event of the various detectors
  Decoding left to detector reconstructions
    Plan to add derived classes to SpecialTrigger class

## Slide 13: Software EOB data
Need to define a format
My proposal, to be implemented soon (KTAG needs it)
  Each producer publishes a data block with two words header
  1st word: bit 31-24 detector ID, bit 23-16 block ID, bit 15:0 block length
  2nd word: EOB Unix time
Detector ID will steer the Pcfarm to put the block in the right detector EOB
Unix time will be used as a consistency check
In addition, use one of the reserved words in the event header to store the offset of the EOB event

## Slide 14: Preparation for the run - 1
Start from now to integrate each detector in the DAQ
  Check initialization through Run Control
  Configure properly for multiple destinations
  Run with a suitable high trigger rate
Define the L0TP configuration
  Inputs
  Possibility of backup NIM-generated primitives
Complete the configuration of the Pcfarm and validate its network configuration

## Slide 15: Preparation for the run - 2
Regularly test the acquisition with CDR recording
Setup in collaboration with IT tools to monitor the network for our needs
Anyway with the output from this meeting, setup a more refined plan for the next weeks
Next iteration:
  TDAQ commissioning meeting on Sep 10th