## Slide 1: Straw Working group
Ferrara 4/9/2014

## Slide 2: Outline
Status and Plans
  Installation of Chambers 1-3
  Chamber 4
  Vacuum test
  SRB
  Readout, monitoring and software
  Passports

## Slide 3: Last preparations on Chamber 4 in 154

## Slide 4: Powering up Chamber 1 in ECN3

## Slide 5: Installation of chamber 1-3

## Slide 7: Summary
7
Number (Ch/Mod/ Coordinates) | Start of assembling | End of assembling | End of testing | Delivered to CERN | Assembling and testing time (months)
CH2 M1 U-V | 09.2012 | 04.2013 | 10.2013 | 11.2013 | 11
CH2 M2 X-Y | 07.2013 | 01.2014 | 02.2014 | 04.2014 | 8
CH4 M1 U-V | 12.2013 | 02.2014 | 03.2014 | 04.2014 | 4
CH4 M2 X-Y | 02.2014 | 05.2014 | 06.2014 | 07.2014 | 4

## Slide 8: Straw production line
Microscope pictures of a straw cross- section for quality control of the weld
Humidity and temperature
control at clean room
Common view of
the Clean room
ISO clean room standard 6
600 mm
On-line control of a weld seam by the digital microscope (zoom x20 on a PC monitor)
Unique welding machine
8

## Slide 9
Summary of straw mass production
Parameter of the quality control Rejected straws
Straw quality vs roll of Mylar tape
6740 2.7 m straws have been produced
Length of a roll: 300 m 250 m

## Slide 10
Tooling
High-intensity light source
Digital microscope
Wire image in a straw
in reflected lite
The same optical ruler
as was used for straw
position measurement
Two high-intensity
light sources

## Slide 11
Module 8 (X-Y):
measurement of distances between wires inside straws
X-plane, layer 1:
Chart: 
| -200.0 | -160.0 | -120.0 | -80.0 | -40.0 | 0.0 | 40.0 | 80.0 | 120.0 | 160.0 | 200.0
Bottom, -90 cm 0 | 0 | 1 | 1 | 6 | 6 | 8 | 2 | 0 | 0 | 0 | 0
Middle, 0 cm 0 | 1 | 1 | 3 | 13 | 32 | 25 | 0 | 0 | 0 | 0 | 0
Top, 85 cm 0 | 1 | 0 | 5 | 11 | 6 | 12 | 2 | 0 | 0 | 0 | 0
Chart: 
Bottom, -90 cm | -28 | 1 | -59 | 35 | 37 | -13 | -101 | 77 | -64 | 73 | -6 | -50 | 26 | 44 | -120 | 76 | 17 | -1 | 58 | -64 | -56 | 3 | 71 | 6 | -9 | 35 | -65 | 75 | 102 | 43 | 64 | -29 | 41
Chart: 
Chart: 
Top, 85 cm | -10 | 20 | -18 | 29 | -41 | 75 | -3 | -103 | 110 | 7 | -65 | 33 | -46 | 29 | -50 | 78 | 36 | 19 | -191 | 145 | -13 | -59 | 76 | -84 | 10 | 28 | -43 | 65 | -118 | 122 | -107 | 58 | -57 | 98 | -75 | 75 | -53 | 57 | -59 | 31 | -16 | -15 | 16 | 72 | -105 | 72 | -48 | 50 | 9
49 wires
97 wires
33 wires
RMS for wire positions – 40 ÷ 50 mm

## Slide 12
Straw tracker – Carioca 1-16 ch. output analog signal
MPOD Universal Low and High Voltage Power Supply System
Amplifer
ADC
PC monitoring gas gain (LabView, C++)
Straw gas gain monitor
High Voltage Power Supply
feedback system

## Slide 13: Status Vacuum System
Decay tube (Sector 5)
Vacuum instruments installation completed
Remote control of all instruments (apart cryopumps) ready
Pressure reached during Decay tube commissioning:
1.2E-6 mbar (decay area)
3.2 E-6 mbar (straw area)
Still water outgassing dominated.
No major leaks on system, neither on vacuum tank nore on Straw system.
Berthold Jenninger
5376 straws!

## Slide 14: Passport (Ch1)

## Slide 15: Summary and plans (Peter)
HV connectors assembly on 3 chambers is on-going
Data cables for 4-th chamber ordered
  Possibly delivered end of the next week
  Cable installation critical
Final installation of VME crates in racks and cable routing next week
3 MPODs should arrive next week
  Installation and integration in DCS (Serguei S.)
Patch panel power supplies arrived
  Johan preparing software for control and monitoring
  Install them in a crate shelf
We have to re-do cover test bench and install it in 154
Small scale readout system in 154
SRB
  Originally we expected all assembled boards at CERN now
    50 PCBs produced in July
    2 assembled at CERN
    Problem with 1 type of FPGA and EPROM
  We secured enough components for 24 boards
    Should arrive to CERN assembled next week – assembly started
    Enough for 3 chambers fully equipped
    Equip 1 chamber first and do the noise scans and cosmics
  The rest of FPGA should arrive to CERN after 11.9.2014 – received 2 deliveries this week
    The rest of boards could be ready in 3 weeks – first/second week of October
    Testing 1 week
    Ready for installation ~15.10.2014
  Firmware/software development continues (and probably will for a long time)
    Cover readout next week
    Data to pc-farm as soon as we have more boards

## Slide 16: Conclusions and Plans (Vito)
The first (small) step toward SRB integration within the TDAQ system has been done,
Software will be completed within next 2/3 weeks (at least the main parts),
Run control must be tested text week
Monitoring is not in a good shape but we can have something
Next steps toward October the 6th:
Develop the firmware to send realistic (but still fake) data to PC farm,
Installation of the new SBCs is planned for the next week,
Next week is foreseen a first implementation of RUN control,
Real data in PC farm (~ mid Sept.),
  Coarse time ordering (steps of 25ns) not immediately ready,
L0 matching will be next step,
On line monitoring.

## Slide 17: Summary
The last chamber was completed on 1.08.2014 ! Chamber 1 , 2 and 3 are installed, but not fully cabled yet. Chamber 4 will be in installed in the coming weeks.
Chamber 1,2 & 3 (5376 straws) were part of the vacuum test with final pressure of ~ 3 x 10-6 mbar. All three chambers were connected to the gas system with final gas mixture circulating.
Between now and October 6, the work is concentrated on the SRB and the readout of the four chambers. Firmware , software run control monitoring. No major problem, but still a lot of work.

## Slide 18: Spares

## Slide 19: Garfield
R=-0.006cm