## Slide 1: Assembling of Straw Modules at JINR has been FINISHED!
Yu. Potrebenikov
Straw WG meeting, September 03, 2014

## Slide 2: Summary
2
Number (Ch/Mod/ Coordinates) | Start of assembling | End of assembling | End of testing | Delivered to CERN | Assembling and testing time (months)
CH2 M1 U-V | 09.2012 | 04.2013 | 10.2013 | 11.2013 | 11
CH2 M2 X-Y | 07.2013 | 01.2014 | 02.2014 | 04.2014 | 8
CH4 M1 U-V | 12.2013 | 02.2014 | 03.2014 | 04.2014 | 4
CH4 M2 X-Y | 02.2014 | 05.2014 | 06.2014 | 07.2014 | 4

## Slide 3
3
Features
of the Dubna assembling line

## Slide 4: Straw production line
Microscope pictures of a straw cross- section for quality control of the weld
Humidity and temperature
control at clean room
Common view of
the Clean room
ISO clean room standard 6
600 mm
On-line control of a weld seam by the digital microscope (zoom x20 on a PC monitor)
Unique welding machine
4

## Slide 5
Straw mass production: off-line tests
Stand for tensile strength
measurement
Optical check of seam quality
Straw long term overpressure test (> 1 month as min)
Straw end-plugs
(top with nipple)
Straw storage after 3 bar overpressure test with 1,5 bar overpressure inside
Stand for straw gas leak measurement

## Slide 6
Summary of straw mass production
Parameter of the quality control Rejected straws
Straw quality vs roll of Mylar tape
6740 2.7 m straws have been produced
Length of a roll: 300 m 250 m

## Slide 7
Straw data base and new design
NA62 straw label: NA62TASTDU003525
NA62 – NA62 experiment
TA or TR – Tracker
ST - straw
DU–Dubna, JINR, Russia
CE – CERN (Sefar, Swiss)
003525 – straw serial # (000001-999999)
Barcode and the NA62 Data Base

## Slide 8
Detector production at JINR:
Modules 2,3,7,8
Sealing of the Module elements in a special “Dry room”
Vacuum test of the Module after sealing
The JINR assembling area
with 2 assembling jigs
A Module assembly rotation jig

## Slide 9
Detector production at JINR:
straw assembling and wiring
Straw insertion and fixing in a horizontal position of a module frame
Straw gluing from the top and bottom in a vertical position of a module frame
Wiring in vertical position of a module frame
Top
Bottom
This procedure need 15 days for wire insertion – more than 2 times faster than usually

## Slide 10
Detector production at JINR:
straw positioning test
Laser
Optical ruler
Optical sensor
Optical ruler:
Handenhain
measurement - up to L=4500 mm
accuracy - (1-2) mkm
Stepping motor with raster pattern:
1 step = 10,4 mkm
“Micro Epsilon” Laser sensor:
measurement distance -
L=(30-50) mm
accuracy - 3 mkm
beam diameter – 0.3 mm
INFN
commands
visualization
saving data
Scan indicator
User interface
Example: measurement of a straw shape
and distances between straws in a module view

## Slide 11
Detector production at JINR:
straw pretention test
1500 G
Requirement: F > 1.5 KG  Fr >=65 Hz)
Opto-coupler
Oscilloscope with the FFT function

## Slide 12
Detector production at JINR:
HV and gas leakage test
Requirement:
I < 4 nA at HV = +2200 V
Temp T=(23-25) degree
Humidity H=(35-40) %
Chamber CH2 M1 U-V - HV – OK, L = 0.5 cm3/min
Chamber CH2 M2 X-Y - HV – OK, L = 0.5 cm3/min
Chamber CH4 M1 U-V - HV – OK, L = 0.1 cm3/min
Chamber CH4 M1 U-V - HV – OK, L = 0.1 cm3/min
These tests have been done for last 2 modules simultaneously!

## Slide 13
Wire position measurement
suggested by L.Glonti
performed by T.Enik and A.Kolesnikov

## Slide 14
Tooling
High-intensity light source
Digital microscope
Wire image in a straw
in reflected lite
The same optical ruler
as was used for straw
position measurement
Two high-intensity
light sources

## Slide 15
Module 8 (X-Y):
measurement of distances between wires inside straws
X-plane, layer 1:
Chart: 
| -200.0 | -160.0 | -120.0 | -80.0 | -40.0 | 0.0 | 40.0 | 80.0 | 120.0 | 160.0 | 200.0
Bottom, -90 cm 0 | 0 | 1 | 1 | 6 | 6 | 8 | 2 | 0 | 0 | 0 | 0
Middle, 0 cm 0 | 1 | 1 | 3 | 13 | 32 | 25 | 0 | 0 | 0 | 0 | 0
Top, 85 cm 0 | 1 | 0 | 5 | 11 | 6 | 12 | 2 | 0 | 0 | 0 | 0
Chart: 
Bottom, -90 cm | -28 | 1 | -59 | 35 | 37 | -13 | -101 | 77 | -64 | 73 | -6 | -50 | 26 | 44 | -120 | 76 | 17 | -1 | 58 | -64 | -56 | 3 | 71 | 6 | -9 | 35 | -65 | 75 | 102 | 43 | 64 | -29 | 41
Chart: 
Chart: 
Top, 85 cm | -10 | 20 | -18 | 29 | -41 | 75 | -3 | -103 | 110 | 7 | -65 | 33 | -46 | 29 | -50 | 78 | 36 | 19 | -191 | 145 | -13 | -59 | 76 | -84 | 10 | 28 | -43 | 65 | -118 | 122 | -107 | 58 | -57 | 98 | -75 | 75 | -53 | 57 | -59 | 31 | -16 | -15 | 16 | 72 | -105 | 72 | -48 | 50 | 9
49 wires
97 wires
33 wires
RMS for wire positions – 40 ÷ 50 mm

## Slide 16
Module 8 (X-Y)
measurement at CERN
Y-plane, layer 4:
39 wires
Chart: 1 bar (NO2), 1750 V
| -200.0 | -160.0 | -120.0 | -80.0 | -40.0 | 0.0 | 40.0 | 80.0 | 120.0 | 160.0 | 200.0
1 bar (NO2), 1750 V 0 | 0 | 0 | 1 | 6 | 13 | 13 | 7 | 0 | 0 | 0 | 0
M = 0 mm
RMS = 40 mm
Chart: 1 bar (NO2), 1750 V
| 9.0 | 10.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 17.0 | 18.0 | 19.0 | 20.0 | 21.0 | 22.0 | 23.0 | 24.0 | 25.0 | 26.0 | 27.0 | 28.0 | 29.0 | 30.0 | 31.0 | 32.0 | 33.0 | 34.0 | 35.0 | 36.0 | 37.0 | 38.0 | 39.0 | 40.0 | 41.0 | 42.0 | 43.0 | 44.0 | 45.0 | 46.0 | 47.0 | 48.0 | 49.0 | 50.0 | 51.0
1 bar (NO2), 1750 V | -20.5 | 34.5 | -22.5 | 57.5 | 60.5 | 32.5 | 43.5 | 37.5 | -24.5 | 48.5 | 40.5 | -12.5 | -30.5 | -43.5 | -22.5 | -93.5 | 25.5 | -56.5 | -2.5 | -8.5 | -52.5 | -13.5 | 25.5 | 1.5 | 47.5 | -8.5 | 72.5 | 5.5 | -49.5 | 27.5 | 5.5 | -69.5 | 26.5 | -27.5 | -75.5 | -14.5 | -25.5 | 13.5 | 29.5 | 38.5

## Slide 17
Thank you for attention!