## Slide 1: Status of NA62 straw electronics and services
Peter LICHARD,
Johan Morant,
Vito PALLADINO

## Slide 2: Services
3 chambers wired with HV, LV and data cables
  Still need to arrange them for crates
HV connectors on MPOD side should be finished this week for 3 equipped chambers
Data cables for chamber 4 ordered
  Expected in 2 weeks
  Production 8 days, shipping ???
VME crates
  3 installed in the pit
  Will need to change place in the rack to compensate for cable length
    Chamber 1; cables short, crate at the bottom
    Chamber 2, cables too long, crate at the higher half of rack
VME SBC
  5 Reinstalled with SLC6
  Problems with library and driver versions
Power supplies for powering patch panels arrived
  Will use provided software for control and monitoring for this year run
  Integration to DCS next year

## Slide 3: Services
MPOD
  3 Bins with LV modules ready for some time
  HV modules arrived rather late
  Company moves to new factory with our PS
  Proposed new shipping on the week of 8.9.
  After intervention they promised to ship them sooner

## Slide 4: Covers
3 chambers tested
  1 cover had to be replaced
Johan measured temperature on the chamber with power on and plastic covering chamber, < 25 degrees
Need to rebuild our ‘test rack’ and ‘test bench’
  VME crate from test rack is for chamber 4
  Need to keep test bench alive for (re-) tesing covers
  Take 6U VME crate from the POOL
  Johan will provide injection control and circuitry
  In 154 we will keep
    Complete readout with straw prototype for development
    Cover test bench
    Spare covers, spare SRBs, patch panels (?)
    Components and cables

## Slide 5: SRB
Plans and reality
  Test data format compliance with ALTERA demonstrator board – failed, reason unknown
  Prototype May/June -> July
  Test with TDAQ in August – only simple connectivity with PC-farm
    sending/receiving Ethernet packets
    Software on pc farm (Jonas) will be debugged/extended as soon as we will have enough SRB’s in the pit

## Slide 6: Prototypes arrived – Hooorraaaaaa but…
Tantalum capacitors inverted, causing explosion with real firework
EPROM mounted 180 degrees, shorting power supply

## Slide 7: Full SRB (Straw Readout Board)

## Slide 8
VME
manager
Front-End
(To covers)
Event
Manager
x2 Gb eth
TTCrx
Trigger
Manager
LOOKUP
TABLE
DDR3
DDR3
DDR3
ETH
HISTOGRAM
SRAM
QDR
CLOCK
DELAY

## Slide 9: BASICs
VME slave – modified and tested
Bridges VME <-> master_slow_control <-> slave_slow_control <-> Avalon_vme_master
  Designed to work with vme-style protocol and avalon
  Delayed due to problem of different specs
Clock generation and distribution
  Small problem with our version of TTCRx
TESTED AND FUNCTIONAL

## Slide 10: On-board high speed links 2.5Gb/s
VME manager receives a complete copy of all data
  Histograms
  Dump of (all) data for on-line monitoring
  Lab readout
Event Manager receives all data
  Time sort
  (trigger selection)
  Storage
  Ethernet out to PC farm
  Copy sent to Trigger Manager
All links are bidirectional
  Allows to send the test data to verify the functionality
LINKS TESTED AND FUNCTIONAL

## Slide 11: Communication with covers
ALTERA dropped soft IP for medium speed links in CYCLONE V
They introduced hard macro (real SERDES built on the chip)
After lot of trials and problems with different versions of QUARTUS software it turned out that they provide very few(/unsufficient) clock resources to drive the SERDESes. We need to adjust every link timing as the cable length is different for every cover. We have lost a lot of time ….
Designed our own soft IP for medium speed links
  Test with covers next week of 8.9.2014

## Slide 12: Big volume DDR3 memory 2*2GB + 2GB
Used mainly for high volume, not speed!
20 MHz write/read should be sufficient
Tested with ALTERA memory tool
Remains test with real inputs/outputs

## Slide 14: Asynchronous high speed (10ns) SRAM
Used for storing on-board generated monitoring histograms
80 MHz write/read allows 40MHz read-modify-write operation
Tested

## Slide 15: Ethernet interfaces 2+1
1 + 1 spare for PC-farm data connection
1 for eventual trigger
Tested
Full test with data-formatted packets
More Vito’s talk

## Slide 16: High speed synchronous SRAM - QDR
1 serves as time-remapping machine for data
1 for eventual trigger lookup table
ALTERA IP not suitable for our purposes
  Need to write simple IP for QDR
Not tested

## Slide 17: TTC optical interface
TTCRx tested with LTU and TTCex
Commands received
Our version (not radiation hard batch) shows strange behaviour without optical fibre
  Starts and stops clock output randomly
  Causes confusion in clock selection
Tested

## Slide 18
Si5338
TTCRX
BUFFER
With
AUTO
SWITCH
Si53302
Si5338
XTAL
25 MHz
TTC
Si5338
Si5338
Si5338
Si5338
4x
D
E
T
E
C
T
O
R
50 MHz
125 MHz
40.07658 MHz

## Slide 19: I2C control of clock delays
T0 adjustment for all links
Not tested yet

## Slide 20: Summary and plans
HV connectors assembly on 3 chambers is on-going
Data cables for 4-th chamber ordered
  Possibly delivered end of the next week
  Cable installation critical
Final installation of VME crates in racks and cable routing next week
3 MPODs should arrive next week
  Installation and integration in DCS (Serguei S.)
Patch panel power supplies arrived
  Johan preparing software for control and monitoring
  Install them in a crate shelf
We have to re-do cover test bench and install it in 154
Small scale readout system in 154
SRB
  Originally we expected all assembled boards at CERN now
    50 PCBs produced in July
    2 assembled at CERN
    Problem with 1 type of FPGA and EPROM
  We secured enough components for 24 boards
    Should arrive to CERN assembled next week – assembly started
    Enough for 3 chambers fully equipped
    Equip 1 chamber first and do the noise scans and cosmics
  The rest of FPGA should arrive to CERN after 11.9.2014 – received 2 deliveries this week
    The rest of boards could be ready in 3 weeks – first/second week of October
    Testing 1 week
    Ready for installation ~15.10.2014
  Firmware/software development continues (and probably will for a long time)
    Cover readout next week
    Data to pc-farm as soon as we have more boards

## Slide 21: Summary and plans
in the next 2 weeks
  A lot of material will arrive
  Manpower from Dubna (Sergei M., Sergei Sch, Dmitri)
  We should finish chamber 4 installation
  Define procedure for T0 adjustment
  Define online and offline monitoring
    What MUST be done on SRB
    What can or can’t be done on SRB
    What must be done on PC
    How often and how much raw data we should store through VME interface for monitoring
  Data analysis
    Feedback on detector performance
    Scan thresholds
    Scan HV
  Write and debug Run Control and local DAQ