## Slide 1
KM3NeT-IT
The Capo Passero Infrastructure
M. Anghinolfi – site manager

## Slide 2
Site:
36° 16’ N, 16° 06’ E,
about 40 NM from shore
depth of 3350 m;
Shore station:
Harbor of Porto Palo
100 km from Catania
electrical supply up to 800 kVA
UPS up to up t 159 kVA
Adequate for system expansion
fibre connection at 1 Gbps to LNS
communication is inserted inside the GARR-X network
The present status : on-shore
Power Supply
Output voltage: 0-10 kV DC
Output current: 0 -5 A

## Slide 3
... and off-shore
Cable termination frame
Unfolds the main cable to 3 ROV mateable output ports
converts the supplied voltage (-10 kV DC) to 375V DC up to 10kW
8 out of the 20 optic fibres of the main cable are available at the 3 outputs
8 floor tower connected to one output on march 2013
Tower prototype
8 Floor 8m length , 40 m spacing
4 10” PMTs per floor
Main cable:
Length (Km): 100
Max Voltage: 10 kV DC
Max Current: 8 Amp
Number of fibres: 20

## Slide 4
Bioluminescence activity in the site from the tower prototype
Continuous monitoring since March 2013
Mean 1 pe counting rate on 10”PMTs: ~ 50/65 kHz (40K)
Burst fraction (>100kHz): 1-2 %
bio sound continuous monitoring
Sea current velocity: low to moderate (average 2-3 cm/s)
Blue: median of rate distribution in 15’
Red: burst fraction %
Single rate on a couple of 10’’ PMTs in floor 1: average values from a 9 months continuous monitoring
PDF evaluate in 1 kHz bin
Low (<10%) probability to have average rate higher than 70 kHz
Very low bioluminescence activity during the 9 month period of operation

## Slide 5
KM3-IT PHASE 1.
PON Poject:
Funded by 20 MEuro to be spent before November 2014
Aimed at the realization of a seabed infrastructure and a first DU block in the site
  compatible to the available 8.5 kW power and exploiting the 20 optic fibres
  composed by:
    8 towers “a la NEMO” (14 floors with 6 10” PMTs per foor)
    24 strings with 18 DOMs
    Sea bed network to connect to the DUs composed by:
      NEW Cable Termination with 5 outputs
      Interlink cables
      4 Secondary Junction Boxes :
        1 SJB for the 8 towers
        2 SJBs for 12 + 12 strings
        1 SJB for EMSO

## Slide 6
The Layout
CTF: Cable Termination (Frame)
: Secondary Junction boxes
: Tower DU
: String DU
EMSO node
Result from various compromises:
Sea deployment operations constraints
Optimized detection efficiency
DC/DC converter power limitation (8.5 kWt)
Uncertainty on the schedule of the
NEW Cable Termination

## Slide 7
Some news on tenders &P.O.
Sea operations
Public tender end of January: assigned to MTS-FUGRO ~ 2.5 M€
Grand total of: 50 days of sea operations including
DRY electro and optical cables
Public tender 18/02: assigned to SEACON ~ 2.5 M€
Backbone for towers, cabling for towers and JBs
Interlink and jumpers for DUs
Public tender completed & proposed assignement to ODI on 04/03. ~ 3.5 M€

## Slide 8
Long interlink cables from CTF to JBs
Purcease order to ODI . Quote almost ready . Will be
finalized during OCEANOLOGY 2014 this week in London
LASERS
Purchease order for full equipement of 8 towers and 30 strings to TALLGRASS
TALLGRASS is available for both Oesolution and Eoptolink
Total amount of 0.6M€
Tender should be approved in April
and in addition…
Tender are on going for CLB, DOM, SUPPORT SYSTEM (see Marco C.)
Mechanical srtucture of towers
Public tender for full structure of the towers including buoy, story and anchor:
assigned end of February 0.6 M€

## Slide 9
MINUTE DALL’ULTIMO SC di km3-IT del 20/03
Papaleo riassume brevemente lo stato degli ordini e gare. Ad oggi risultano già impegnati circa 17.3 M€. A breve partiranno ancora due ordini, quello dei laser ( circa 0.55M€) e quello alla ODI sui cavi lunghi di interlink e connettori del nuovo CTF (circa 1.3M€).

## Slide 10
Integration
OMs:
effettuato nei locali del laboratorio INFN al porto
02/04: inizia saldatura 550 basette alimentazione – PMT
30/04: arrivano FEM, mu metal e sfere
01/05: inizia assemblaggio MO; rate previsto : 4 MO/die
FCM:
FCM vessel: produzione terminata
FCM schede: consegna primi di giugno (ordine arrivato venerdi scorso)
PSS: consegna metà maggio
Transceiver: in poco tempo consegnino solo x fare 2 torri. I restanti a novembre.
Connettori: ordinati
Le sezioni di PI e LNS faranno l’integrazione e i test. Rate previsto: 2 moduli/die/sezione.
TOWERS…
Meccanica: in fase di produzione, primo prototipo del piano prossima settimana. Ritmo di produzione previsto non meno di due piani al giorno.
Cavi , connettori, sensori: ordinati. Sono state fornite alle ditte liste di priorità congruenti con l'integrazione di almeno una torre ed una JB prima dell'estate.
Siti integrazione: LNS, Frascati: l'integrazione della prima torre è programmata con inizio nella seconda metà di giugno e termine entro 15 gg. dall'inizio

## Slide 11: Possible scenario (end 2014)
MVC
3 O + 2 E
3 O + 2 E
2 O + 2 E
With 3 fibers will be possible only to install 4 towers
With 3 fibers will be possible only to install 8 strings
OR

## Slide 12: Final configuration with New CTF (end 2015)
New CTF
4O + 2 E
4O + 2 E
4O + 2 E
4O + 2 E
4O + 2 E
It will be possible to install all the towers (8)
It will be possibile to install until 12 strings
It will be possibile to install until 12 strings

## Slide 13
Major Milestones
PPM DU deployment & connection: May 2014
Deployment & installation of manifold: fall 2014
Recovery of the PPM DU and tower : fall 2014
Deployment & installation of 2 SJBs: fall 2014
Procurement of interlink cables (before November 2014,
contractual clause)
Tower installation: end 2014
One DU string ready for deployment : end 2014
Part of DU string installation: spring 2015
New Cable termination: mid 2015

## Slide 14
Summary
Capo Passero: shore station in operation and suitable for system expansion
Site: clean & calm during 11 months monitoring
Phase 1: install network for 8+24 DUs
Severe constraints on:
  Expenditure time profile
  procurement of cable termination