## Slide 1: SPES status
2° Meeting of the SPES Technical Advisory Committee
Gianfranco Prete
Project leader
LNL, December 4th 2014
BOZZA

## Slide 2
SPES Strategy
a
d
b
g
BEST Cyclotron installation & commissioning:
70 MeV proton beam
750 mA
Research and Production of Radio-Isotopes for Nuclear Medicine
Production & re-acceleration of exotic beams, especially neutron–rich from p-induced Fission on UCx
Accelerator based neutron source (Proton and Neutron Facility for Applied Physics)
LARAMED
Second generation ISOL facility
Toward
Notes: The SPES strategy was already presented many times: it is related to the division of the project in phases which are independently financed.
The alpha phase which is gonna to be quickly completed refers to the construction of a new building for the installation and commissioning of a newly developed commercial Cyclotron from the BEST company characterized by a variable energy (30-70 MeV) and a very intense proton beam (up to 750 microA) .
The beta phase is related to the production and post-acceleration of exotic beams produced mainly through the fission induced by the intense protion beam on a sliced UCx target.
Phase gamma concerns with th research and production of radio-isotopes fro Nuclear medicine (the so-called LARAMED project)
Finally phase delta is related to the use of p or n beams for applications for material studies or electronics damage study etc.

## Slide 3
PRISMA
GALILEO
*Fazia
**CHIMERA
TRACE
GARFIELD
*NEDA
*AGATA
RIPEN
*PARIS
Presented 37 Letters of Intents
Chart: SPES LOIs Topics
| GS properties | moments | Coulex | DirReac with ActiveTarget | DirReac with Si | Mn transfer | Collective ex | Fusion | Super Heavy | Dymanics
SPES LOIs | 3 | 1 | 5 | 2 | 5 | 3 | 5 | 4 | 2 | 4
Chart: SPES LOIs Spokespersons
| Italy | France | Poland | Russia | USA | Belgium | Croatia | Norway | Bulgaria | Spain | Russia | China
SPES LOIs | 12 | 6 | 6 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1

## Slide 4
SPES up-grade:
High level «European» instrumentation
Second ISOL bunker and High intensity
High resolution mass separation at 1/40000
Reaccelerated beam energy upgrade
  New cavities for ALPI
  New EBIS Charge Breeder with up to date performances
Curtesy M.Lewitowicz

## Slide 5
Existing facility
ALPI
3° Exp.Hall
Tandem
SPES Facility Layout
70 MeV 0,75 mA
Proton cyclotron
 | SPES sub-systems
1 | Building and infrastructures with 2 ISOL bunkers for radioactive beam and application area for radioisotopes and neutrons
2 | Cyclotron 70 MeV protons with 2 independent exits
3 | ISOL UCx target designed for 1013 f/s
4 | Beam transport with High Resolution Mass Separation
5 | Reacceleration with ALPI superconducting linac (10A MeV A=130)
6 | Radioprotection, safety & controls
1
2
Target under operation at 2000oC
5
4
Control system
6
3
3

## Slide 6
Existing facility
ALPI
3° Exp.Hall
Tandem
Infrastructures
2
Target under operation at 2000oC
5
4
Control system
6
3
3
1
 | SPES sub-systems
1 | Building and infrastructures with 2 ISOL bunkers for radioactive beam and application area for radioisotopes and neutrons
2 | Cyclotron 70 MeV protons with 2 independent exits
3 | ISOL UCx target designed for 1013 f/s
4 | Beam transport with High Resolution Mass Separation
5 | Reacceleration with ALPI superconducting linac (10A MeV A=130)
6 | Radioprotection, safety & controls

## Slide 7
Today
One year ago
cyclotron
LARAMED Radioisotope production area
NEPIR
Neutron area
SPES building construction
WORK in progress
Milestones to accept cyclotron :
1. Delivery of building Feb 28, 2015
2. Delivery of infrastructures Apr 30, 2015
ISOL facility
Notes: Date indicate valide per posa ciclotrone e infrastrutture ciclotrone. Consegna edificio e chiusura cantiere fine settembre (v. Calderolla)

## Slide 8: LARAMED Project
Joint Research lab of INFN, CNR, Universities and external companies:
Measurement of cross section through targets activation
High power targets tests
Radioisotopes/radiopharmaceuticals Production test facility (99mTc, 64Cu, 67Cu, 82Sr, ...)
Production laboratory in conjunction with external companies:
Selected isotopes of medical interest
Funded with 6.8 Meuro
STATUS:
Building and infrastructures development
Design of radiochemistry labs
Design of beam line and target management
Contract with company for radioisotopes production to be finalized

## Slide 9: Temporary A3-A4 installation
Operation allowed by SPES alpha authorization (500mA, 70MeV in the limit of rad.prot. rules)

## Slide 10
Existing facility
ALPI
3° Exp.Hall
Tandem
Cyclotron
70 MeV 0,75 mA
Proton cyclotron
 | SPES sub-systems
1 | Building and infrastructures with 2 ISOL bunkers for radioactive beam and application area for radioisotopes and neutrons
2 | Cyclotron 70 MeV protons with 2 independent exits
3 | ISOL UCx target designed for 1013 f/s
4 | Beam transport with High Resolution Mass Separation
5 | Reacceleration with ALPI superconducting linac (10A MeV A=130)
6 | Radioprotection, safety & controls
1
Target under operation at 2000oC
5
4
Control system
6
3
3
2

## Slide 11
Cyclotron test at BEST Company site (Ottawa)
Main Parameters | 
Accelerator Type | Cyclotron AVF 4 sectors
Particle | Protons (H- accelerated)
Energy | Variable within 30-70 MeV
Max Current Accelerated | 750 µA (52 kW max beam power)
Available Beams | 2 beams at the same energy (upgrade to different energies)
Max Magnetic Field | 1.6 Tesla
RF frequency | 56 MHz, 4th harmonic mode
Ion Source | Multicusp H- I=15 mA, Axial Injection
Dimensions | Ф=4.5 m, h=1.5 m
Weight | 150 tons
Cyclotron assembled and operated with 700 mA at 1MeV
In the factory at Ottawa, the construction and the assembly of the Cyclotron is completed. The assembly of the RF resonators is over and the injection and acceleration phase started according to the schedule (1 MeV at full current).
FAT partially approved on November 29th
Notes: In particular on last May some tests have been performed on the source. Some of our engineers have been participating to the test at BEST in Vancouver and they could certify the succesfull results. Meanwhile in Ottawa the assembling of the Cyclotron was going on: the RF resonators have been assembled and they are now under conditioning. The first checks on the resonance frequency and on the tuning range are according to the specifications. The schedule now foresees the FACTORY ACCEPTANCE TEST during these months after which the shipment will be programmed in the coming Fall.

## Slide 12
Final Fatory Acceptance Test
in Ottawa next week
Test was not completely succesfull, under discussion the following steps (more exaustive test in Ottawa or cyclotron dismounting and transfer to Italy)
See Augusto presentation
Succesful vacuum test: below 10-7 Torr after 2hours pumping
700 mA
current measured at inflector collimator (green), beam stop (blue) and 1MeV probe (red).
Notes: The Figure shows how the current measured at inflector collimator (green curve), beam stop (blue
curve) and 1MeV probe (red curve) are displayed.

## Slide 13
Existing facility
ALPI
3° Exp.Hall
Tandem
ISOL production
 | SPES sub-systems
1 | Building and infrastructures with 2 ISOL bunkers for radioactive beam and application area for radioisotopes and neutrons
2 | Cyclotron 70 MeV protons with 2 independent exits
3 | ISOL UCx target designed for 1013 f/s
4 | Beam transport with High Resolution Mass Separation
5 | Reacceleration with ALPI superconducting linac (10A MeV A=130)
6 | Radioprotection, safety & controls
1
Target under operation at 2000oC
5
4
Control system
6
2
3

## Slide 14
Technical highlights: the production target
SPES DIRECT TARGET CONCEPT to operate with 8 kW proton beam
Target under operation at 2000oC
Direct Target carefully designed to reach 1013 fissions/s with 8 kW proton beam (thermo-mechanical considerations);
In beam test performed at iThemba lab (South Africa) on May 2014;
Prototype under operation.
Fully developed front-end following ISOLDE design;
UCx target completely developed
(A. Andrighetto et al.)

## Slide 15
Target Power test @ iThemba Labs
SPES target in-beam power test (SiC target, operating temperature 1450oC)
Heater power compensated by proton beam.
Up to 4 kW proton beam in target.
Stable temperatures
Stable vacuum
(3 10-5 mbar)
Proton beam
66MeV 60 mA
Tdisk
Tbox
heater
Proton current
Tdisk 1450oC
Tbox 1200oC
Heater power
Thanks to Rob, Lowry and all the iThemba_Labs Cyclotron staff
iThemba_Labs, May 17th, 2014
A.Monetti, J.Vasquez
Notes: The test was performed few months ago at iThemba, within the collaboration between Italy and South Africa on a complete SPES configurated target, bringing up to 4KW on target. Check on the stability of Vacuum and temperature were performed and the test was completely satisfactory. Some more test are planned in the next future.

## Slide 16
Existing facility
ALPI
3° Exp.Hall
Tandem
Beam transport and reacceleration
 | SPES sub-systems
1 | Building and infrastructures with 2 ISOL bunkers for radioactive beam and application area for radioisotopes and neutrons
2 | Cyclotron 70 MeV protons with 2 independent exits
3 | ISOL UCx target designed for 1013 f/s
4 | Beam transport with High Resolution Mass Separation
5 | Reacceleration with ALPI superconducting linac (10A MeV A=130)
6 | Radioprotection, safety & controls
1
5
Control system
6
3
2
4
5
Notes: Nuovo layout

## Slide 17
High Resolution Mass Separator & Beam Cooler
1.3 mm
DM=2.5 10-5
Electrostatic Plates to correct the voltage ripple of the H.V. platform
20 cm
Plates gap 6 cm,
± 750 V to correct
± 5 V platform ripple
10 cm
Typical voltage fluctuation frequency 200-300 Hz, <<10kHz
Scaled-up version of the separator designed by Cary Davids for CARIBU, Argonne
Mass resolution: 1/40000 (eng. design: 1/25000)
High Resolution Mass Separator
Physics Design stage
L.Calabretta, M.Comunian, A.Russo, L.Bellan
COOLBEAM experiment financed by INFN-CSN5, 20122015
Collaboration: LNL-LNS, Mi bicocca
Beam Cooler to match the HRMS input requirements
M.Maggiore
Collaboration SPES – CENBG Bordeaux (SPIRAL2)
Notes: For what it concerns the high resolution mass spectrometer the design of the spectrometer is being studied as an upgraded version of the CARIBU design by Davids in Argonne. However a collaboration with people working on Spectrometers for DESIR is under discussion within the LEA agreement between France and Italy. In order to reach the required selection parameters of 1/20000 engineering design a cooler stage is under study so to reduce the input emittance before the spectrometer as displayed in the slide.
5-6 pi mm mrad da SIS; 30 pi con la PIS; con BC che la fa diventare 3; Delta E è dal Jitter della piattaforma, che non è possibile e quindi si sincronizza il ripple della piattaforma con un campo sul fascio di deflessione in feedback

## Slide 18: HRMS 1+beam line and sinergies with LNS
Possible use of EXCYT components to improve SPES
(items to be discussed)
dipoles for mass selction
High Voltage plateform parts
HV power supply
development of gas recovery system
Collaboration with SPIRAL2 for High Resolution Mass Separator design.
Feasability study for 1+ beam line
Notes: Nuovo layout

## Slide 19: Collaboration agreement with LPSC (Grenoble) for the SPES Charge Breeder
1+ Stable Source
Tape System
Mass Separator
CB
The development of an Upgraded PHOENIX booster is Part of a MoU in the frame of the European Associated Laboratories (LEA-Colliga) with GANIL.
(In exchange: development of SPIRAL2 n-converter by INFN)
Project and construction by LPSC_Grenoble
2010 Preliminary measurements
2011 Conceptual design and schedule definition
2012 Design
2013 Agreement definition
2014 Construction
2015 Commissioning
Charge Breeder development and medium resolution mass separator
T. Lamy (LPSC), A. Galatà (INFN), et al.
Notes: Mettere IN2P3 e LPSC, verifica con Galatà!

## Slide 20
Exotic Beam reacceleration and diagnostics
Mechanical layout of the RFQ
A. Pisent, M.Poggi, T.Marchi
MCP based Low intensity beam monitor
Tape system
Room temperature RFQ
Installation of new High Energy beam line.
(Today under commissioning)
New EPICS control system for diagnostic and magnets
Notes: Fare 1 sola slide con diagnostica + rfq

## Slide 21
The Upgraded Alpi post-accelerator
For stable beams
For exotic beams
Low Beta=5 MV/m, Medium Beta=4.3 MV/m, High Beta=5.5 MV/m
Conservative value: 2 cavities off in the calculation.
M. Comunian
Reshape and improvement of low beta cavities.
Added high beta cryostats to improve the final energy.
Low beta

## Slide 22
Existing facility
ALPI
3° Exp.Hall
Tandem
Rad.Prot, safety & controls
 | SPES sub-systems
1 | Building and infrastructures with 2 ISOL bunkers for radioactive beam and application area for radioisotopes and neutrons
2 | Cyclotron 70 MeV protons with 2 independent exits
3 | ISOL UCx target designed for 1013 f/s
4 | Beam transport with High Resolution Mass Separation
5 | Reacceleration with ALPI superconducting linac (10A MeV A=130)
6 | Radiation protection, safety & controls
1
Target under operation at 2000oC
5
4
Control system
6
3
3
2

## Slide 23
Radioactivity distribution inside SPES beam lines
Figure 14: Z\A plane with the particle currents and the separation places, (brown) WF, (green) 90 deg dipole, (light blue) HRMS (beam cooler losses have been considered). Purple indicates the nominal species.
Selective capability of the SPES mass separators

## Slide 24
Access control description

## Slide 25
Gara sottomessa all’INFN
1.2 Meuro
Radiologic survey system

## Slide 26: SPES Safety TAC Nov 19-20, 2014
R. Catherall (chair) will report tomorrow about findings, comments and recommendations
(debriefing on-going…)
Prioritization of actions on safety and plants for:
Execution of cyclotron SAT tests (from and 2015, see Lombardi)
Exploitation of the cyclotron for Nulear Physics tests and radioisotope production (from 2016)
Explotation of SPES-beta (from 2018)
Notes: Aggiungere una slides con le azioni di Duy

## Slide 27: Planning for final SPES Safety System development
Risk analysis on the way, following the ISOLDE safety roadmap (based also on information on safety systems for similar projects /facilities (e.g. ISOLDE (CERN), ALBA (Spain), ELETTRA (Italy) )
Full design of Safety System with support of external companies
Preliminary contacts with some companies in the field (Siemens, Pilz, Schneider.....)
The goal is to have:
Bid for executive project of Safety System : January 2015
Bid for implemetation of Safety System : June 2015
Notes: Chiarire che è il sistema di sicurezza per SPES-beta, preparato da noi con Safety engineer, sistematizzato a norma di legge con la ditta.

## Slide 28
 | 2012 | 2013 | 2014 | 2015 |  | 2016 | 2017 | 2018 | 2019
Authorization to operate and safety | UCx 5microA |  |  |  |  |  |  |  | 
ISOL Target-Ion Sources development |  |  |  |  |  |  |  |  | 
ISOL Targets construction and installation |  |  |  |  |  |  |  |  | 
ISOL on-line commissioning |  |  |  |  |  |  |  |  | 
Building Construction | Executive project | raw building construction |  |  |  |  |  |  | 
Cyclotron Construction & commissioning |  |  |  | Cyclotron at LNL |  |  |  |  | 
RFQ development and Alpi up-grade |  |  |  |  |  |  |  |  | 
Design of RIB transport & selection (HRMS, Charge Breeder, Beam Cooler) |  |  |  |  |  |  |  |  | 
Construction and Installation of RIBs transfer lines , CB and spectrometers |  |  |  |  |  |  |  |  | 
Stepwise commissioning and first exotic beam (2018), HRMS in 2019 |  |  |  |  |  |  |  |  | 
SPES general planning
Versus TAC1, stretched by 10 months for better planning (see next slide), and by 10 months
due to the addition of the BC+HRMS construction and commissioning
Notes: Anticiperei questa, perché così contestualizzi meglio le spieghe successive dei soldi

## Slide 29: Schedule updated in «Project» (750 tasks)
Main commissioning milestones:
- End 2015: Cyclotron
End 2016: Charge Breeder to RFQ injection (and training on breeding and mass separation)
End 2017 – end 2018: first commissioning of SPES w/o BC and HRMS
End 2019: completion of commissioning w/BC and HRMS (and of the project).
Notes: Verificare se e quanto il ritardato inizio (fondi 2014, 6 mesi dopo) impatta sulla scaletta qui sopra…
Giovanni: verifica planning e fornire a Gianfranco

## Slide 30
Values in Meuro | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Grand Total
Radiation prot, Safety &Controls |  | 0.1 | 1.6 | 3.3 | 0.8 | 0.3 |  | 6.1
INFRASTRUCTURES | 4.5 | 0.3 | 0.5 | 3.1 | 1.1 |  |  | 9.5
CYCLOTRON | 10.7 |  |  | 0.2 |  |  |  | 10.9
EXOTIC BEAMS | 0.9 | 0.8 | 0.5 | 0.9 | 0.8 | 0.1 |  | 4.0
BEAM TRANSPORT | 0.5 | 0.2 | 3.3 | 1.5 | 5.8 | 1.8 | 0.7 | 13.7
Re-ACCELERATOR | 1.9 | 0.4 | 0.9 | 3.0 | 0.7 | 0.2 |  | 7.2
 | 18.5 | 1.9 | 6.7 | 11.9 | 9.2 | 2.3 | 0.7 | 51.2
SPES subsystems and construction cost for each subsystem
SPES funding plan
*HRMS (2,7M€) included, residue of bid for building (2M€) included

## Slide 31
(kEuro) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
Total SPES 2013-2018 32.660 kEuro | 1.860 | 6.800 | 11.900 | 9.100 | 2.300 | 700
Economic planning for SPES construction 2013-2018
*HRMS (2,7M€) included, residue building (2M€) included
Chart: 
| 2013 | 2014 | 2015 | 2016 | 2017 | 2018
INFN | 4500000 | 9488481.44 | 8380198.86 | 2299319.7 | 700000
Sinergia con altri progetti INFN | 2400000 | 800000 | 0 | 0
Premiale2011 | 1864000 | 2300000

## Slide 32
Chart: 
| 2013 | 2014 | 2015 | 2016 | 2017 | 2018
WP-B1 - Scientific Support and Nuclear Diagnostics | 7 | 83 | 100 | 0 | 0 | 0
WP-B2 - Safety and Radioprotection | 32 | 500 | 1193 | 595 | 595 | 0
WP-B3 - Buildings and Plants | 340 | 200 | 750 | 150 | 0 | 0
WP-B4 - Cyclotron | 0 | 200 | 100 | 0 | 0 | 0
WP-B5 - ISOL system | 860 | 100 | 1550 | 100 | 70 | 0
WP-B6 - Beam transport &selection | 41 | 2700 | 5195.5 | 2045.5 | 1000 | 0
WP-B7 - RNB Accelerator | 434 | 1665 | 1783 | 1750 | 800 | 0
WP-B8 - Vacuum systems | 100 | 1550 | 0 | 0 | 0 | 0
WP-B9 - Control | 67 | 640 | 0 | 0 | 0 | 0
WP-A1 - Management | 77 | 250 | 130 | 110 | 110 | 0
CORE SPES funding plan
2014 Budget: 50% Available
(also subject to TAC evaluation)
As presented at TAC1
Main differences: beyond the 4,5 M€ (?) of Prize Project

## Slide 33
Existing facility
ALPI
3° Exp.Hall
Tandem
Main bids 2014
Main Bids 2014 | (k€)
Bid for radioprotection surveillance Bid for control system network Bid for beam transport components (CB to end of ALPI) Bid for cryogenics upgrade Bid for vacuum system (CB-Alpi injection) Bid for additional bunkers doors Bid for Laser source | 1100 400 1500 800 1200 700 500
Beam transport
Shielding doors
Vacuum system
Available funds 2014: 6.8 Meuro
(4.5 of them assigned at end of October)

## Slide 34
Tentative schedule for the subsequent phases of cyclotron acceptance tests and operation
First phase of cyclotron installation and operation (beginning of SAT tests).
April 2015 expected Cyclotron at LNL
Building and infrastructures required for the cyclotron operation should be in place.
January-April 2015:
  Validation of the safety aspects of the technical specifications regarding the cooling and ventilation system that will be delivered in April 2015 (e.g. redundancy, interlocks, emergency procedure).
  Design of the high-power beam dump (35 kW) and preliminary risk analysis for tests execution at low and high power beam.
  Definition and set-up of the storage location for the beam dumps (low and high power) after acceptance test.
  April-September 2015:
    Cyclotron installation.
    Delivery of radiation protection surveillance system (consistent with ongoing order procedure).
    Construction of high power beam dump.
    Evaluation of ventilation system with doors installed.
Notes: In April 2015 the building+infrastructures required for the cyclotron operation should be in place. As in the presentation to TAC2.
January-April 2015: Validation of the safety aspects of the technical specifications regarding the cooling and ventilation system that will be delivered in April 2015 (e.g. redundancy, interlocks, emergency procedure)
January-April 2015: final design of the low-power beam dumps (10-16 kW); preliminary risk analysis of the tests done on the low (and high) power beam dumps
RP simulations on radiation and air+water contamination will be carried out following the previous steps for the low-power beam dump, to be calculated to see if we can reach the SPES-beta specs (40 MeV, 200 uA)
January-April 2015: Definition of the storage location of the 2 beam dumps (low (and high) power) after acceptance test
About at the same time the cyclotron will be delivered (April 2015), so we can guess that we can assemble and hardwire it by September 2015
By September-October we should receive the system for radiation monitoring (consistent with ongoing order procedure).

## Slide 35
Tentative schedule for the subsequent phases of cyclotron acceptance tests and operation
Expected situation in October 2015 for starting Cyclotron operation
ISOL bunker completed with shielding and air tight doors and ready to host the beam dump.
Absence of access control system will be managed by locked doors when the beam is on.
Production of contaminated air will be controlled by radiation density monitor on the outer chimney, with a feedback on the cyclotron on/off state if the threshold is reached (1Bq/gr).
    All the above allows us to carry out first tests with the proton beam from the cyclotron in very preliminary and temporary conditions.
Notes: Situation expected in October 2015, if the above is carried out as planned:
All the above allows us to carry out first tests with the proton beam from the cyclotron in very preliminary and temporary conditions, anyway the tests will be interesting and useful. Conditions will be the following:
Absence of access control system will be managed by locked doors when the beam is on
Production of contaminated air will be controlled by radiation density monitor on the outer chimney, with a feedback on the cyclotron on/off state if the threshold is reached
Preliminary means that we can reach a power compatible with our need for nuclear physics experiments (40 MeV out of 70, and 200 uA out of 700 on SiC, with respect to cyclotron specs and what is to be done in the SAT – Site Acceptance Tests).
IMPORTANT: all the above assumes that we are able to limit the air intake to the “hot” bunker to 50 m3/h or less, otherwise the release into the chimney will be much higher and the proton current limit much lower. Feasibility of this conditions should be checked with similar practical examples anywhere else. BUT: With max intake of 50m3/h, on graphite, one can stay below 1 Bq/g by mixing 100 m3/h from other areas of the building directly into the chimney (allowed) and, according to radioactivity production calculations, even reach the SAT specs (70 MeV and 500 uA).

## Slide 36
Milestones | Main Bids | (k€)
1- Building and plants completed 2- Cyclotron: delivery, installation and SAT 3- Commissioning of target remote handling system 4- Commissioning of diagnostic box prototype 5- Charge Breeder installed 5- RFQ engineering design completed 6- Installation of access control system 6- Commissioning of Radioprotection surveillance | Bid for ISOL laboratory and hot cell Bid for transport system (BC, 1+line, MRMS-platform, diagnostic) Bid for RFQ materials and RF System Bid for access control system Bid for Safety System Bid for control of RF, diag, transp Partial payment of building | 2900 1500 1900 600 1200 1500 1000
2015 Milestones and bids
(index refers to SPES components)
Funds 11.900 kEuro

## Slide 37: SPES personnel plan
SPES personnel in 2014
Personnel involved: about 70 persons
46 FTE
It was 68 persons, 44 FTE in TAC1
Chart: 
| management | scientific support | Mecc.Engineering | vacuum systems | safety-radioprotection | infrastructures | controls | cyclotron | ISOL beams | beam transport and selection | rfq | Re-acceleration
staff | 5 | 5 | 4 | 2 | 2 | 7 | 4 | 1 | 3 | 4 | 3 | 5
Temporary | 1 | 1 | 4 | 2 | 3 | 1 | 6 | 1 | 9 | 1 | 1 | 4
Chart: 
| management | scientific support | Mecc.Engineering | vacuum systems | safety-radioprotection | infrastructures | controls | cyclotron | ISOL beams | beam transport and selection | rfq | Re-acceleration
FTE_staff | 2.2 | 1 | 1.6 | 0.6 | 1.3 | 2.4 | 2 | 0.7 | 1.5 | 2.9 | 1.1 | 2.2
FTE_Temporary | 1 | 1.5 | 3.7 | 0.8 | 1.5 | 1 | 5.5 | 0.8 | 5.3 | 1.5 | 0.3 | 2.3
45 (18 FTE) staff
8 (7 FTE) temporary contracts
21 (21 FTE) training

## Slide 38: Personnel for cyclotron operation and management
Responsible (Tecnologo/Ricercatore II liv)
RF engineer (Tecnologo III liv)
Accelerator Physics (Ricercatore/Tecnologo III liv)
RF technician
Diagnostic and control technician
Vacuum/mechanics technician
N.6 Machine Operators
6 units in 2015 and 6 in 2016
Notes: In English.

## Slide 39: Management Challenges and Weaknesses
Decreasing lab personnel for government restrictions;
Overlap with projects with equivalent priority (IFMIF, then ESS, …) with critical people in critical positions in both;
Lacking people/competences:
  Effort to maintain strategic competences using turn over
  Lack on Management and administration (quality management, project management, project secretariat, project administation)
  Steep increase in everyone’s committments leaves too little room for: meetings (MB, project team, …); appropriate preparation of documents;
  (system integrator started, but at the moment with strong committment on IFMIF…) – TO BE FIXED ASAP
Notes: Equivalent priority ==undefined priority; SPES schedule considers FTEs, taking into consideration such multiple committments, but various schedules are not yet harmonized

## Slide 40
Additional slides

## Slide 41
SPES workshop
Building
Cyclotron
ISOL power test
Safety strategy
Milestones
Funding
personnel
Notes: Ho visto che è piuttosto efficace ciò che presenta Kester al FAIR MAC e ti propongo qualcosa di simile: prima metà del talk in cui passi in rassegna tutta la macchina con i principali achievements di tipo tecnico, risultati ottenuti, pezzi acquistati, pezzi montati. In questo senso potresti passare in rassegna la macchina tipo il talk che mi hai preparato per lunedì e che ho leggermente modificato.
Poi la seconda parte gestionale.

## Slide 42
SPES layout
=1/1000
RFQ ----- MRMS – CB --- 1+ RIB line ----- HRMS -- BC ------ISOL-----Cyclotron
=1/20000
=1/200
Notes: O la 6 o la 7, nuovo layout!

## Slide 43
Cyclotron criticalities
Factory Acceptant Test: Ottawa 24-28 Nov 2014
Delivery a LNL started : 5 Feb 2015
Delivery to LNL completed: 28 Feb 2015
Installation : 2 months
Site Acceptance Test: within Sep 2015
Critical points:
Synchronize delivery, installation and tests of cyclotron and beamline with building and plants for SPES-alpha phase
Personnel
Logistic support from LNL to BEST for installation
Technical support from LNL to BEST for hardware tests and commissioning (SAT)
Detailed agreement on SAT (updated agreed upon version), with particular concern for critical components as beam diagnostics and high-P beam dumps

## Slide 44: Beam Diagnostics

## Slide 45
Exotic Beam reacceleration: room temperature RFQ
1+ Stable Source
Magnetic Line with
Magnets and Solenoids
Tape System 2
RFQ
CB
MRM Spectrometer
Mechanical layout of the RFQ
Energy 5.7  727.3 [β=0.0395] KeV/A (A/q=7)
Frequency 80 MHz
Beam transmission >95%, low RMS longitudinal emittance at output: 0.15 ns*keV/u.
Length 695 cm (7 modules) intervane voltage 63.8 – 85.8 kV
RF power (four vanes) 100 kW.
Mechanical design and realization, taking advantage of IFMIF experience (LNL, INFN_Pd, Bo, To).
E. Fagotti, A. Pisent
Physics design
High power RF Coupler 200kW 100% duty cycle
Notes: Fare 1 sola slide con diagnostica + rfq

## Slide 46: SC Resonator Improvements on ALPI
LOW-BETA
UPGRADE

## Slide 49
Work Pakage | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Grand Total
WP-B1 – Scientific support | 0.0 | 0.0 | 0.0 | 0.3 | 0.2 | 0.0 | 0.0 | 0.5
WP-B2-Radiation Protection and Safety (1,9) | 0.0 | 0.0 | 1.3 | 1.3 | 0.0 | 0.0 | 0.0 | 2.6
WP-B3 - Infrastructures | 4.5 | 0.3 | 0.5 | 3.1 | 1.1 | 0.0 | 0.0 | 9.5
WP-B4-Controls | 0.0 | 0.1 | 0.3 | 2.0 | 0.8 | 0.3 | 0.0 | 3.5
WP-B5 - Cyclotron | 10.7 | 0.0 | 0.0 | 0.2 | 0.0 | 0.0 | 0.0 | 10.9
WP-B6- Exotic Beams | 0.9 | 0.8 | 0.5 | 0.9 | 0.8 | 0.1 | 0.0 | 4.0
WP-B7 - Beam Transport | 0.5 | 0.1 | 2.0 | 1.1 | 3.2 | 1.5 | 0.7 | 9.0
WP-B8 - RFQ | 0.0 | 0.0 | 0.0 | 1.9 | 0.3 | 0.1 | 0.0 | 2.3
WP-B9 - Re-Accelerator | 1.9 | 0.4 | 0.9 | 1.1 | 0.4 | 0.1 | 0.0 | 4.8
WP-B10 - Mechanics | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.1 | 0.0 | 0.2
WP-B11 –Vacuum systems | 0.0 | 0.1 | 1.3 | 0.1 | 2.4 | 0.2 | 0.0 | 4.0
 | 18.5 | 1.9 | 6.7 | 11.9 | 9.2 | 2.3 | 0.7 | 51.2
SPES Economic planning

## Slide 50
Milestones and bids up to the end of the project
Year | INFN provision (k€) | Milestones (index referred to SPES components) | Main Bids (k€)
2016 | 8.300 | 2- Cyclotron in operation 3- Installation ISOL target and ion source system 3- Design of target storage system 4- Commissioning of Charge Breeder and MRMS 4- HRMS engineering design completed 6- Safety system for cyclotron operation available | Bid for tape station (500) Bid for second part of vacuum system and gas recovery system (2500) Bid for transport components (ISOL to CB) (1600) Bid for Diagnostic boxes (1+ beam line ISOL to CB) (700) Bid for low frequency bunchers (385) Bid for Beam Cooler (700) Partial payment building (1000)
2017 | 2.300 | 3- ISOL laboratory and hot cell completed 3- Commissioning of ISOL system and 1+ beam 5- Low frequency bunchers available 6- Machine Protection system completed 6- Authorization process for UCx operation completed | Bid for HRMS
2018 | 700 | 3- Commissioning of Laser laboratory 4- Commissioning of Beam Cooler 5- Commissioning of RFQ | Bid for HRMS platform
2019 |  | 4- Commissioning of HRMS SPES full operation with reacceleration of purified neutron rich beams | 

## Slide 51
2014/2 | Cyclotron Factory Acceptance Test (FAT) completed
2014/2 | Start authorization request for UCx target irradiation
2015/1 | Building and plants completed
2015/2 | Commissioning of Radioprotection surveillance
2015/2 | Cyclotron Acceptance Test (SAT) completed
2015/2 | RFQ engineering design completed
2016/1 | Safety system for cyclotron operation available
2016/1 | Installation ISOL front end and ion source system
2016/1 | Commissioning of Charge Breeder and MRMS
2017/1 | HRMS engineering design completed
2017/2 | Commissioning of ISOL system and 1+ beam
2018/1 | Commissioning of RFQ
2018/1 | Commissioning of 1+ beam line
2018/1 | Authorization process for UCx operation completed
2018/2 | Commissioning of ALPI reacceleration for radioactive beams
2019/1 | Commissioning of HRMS
SPES main milestones

## Slide 52
Milestones | Main Bids | (k€)
1- Row building construction completed 2- Cyclotron Factory Acceptance Test (FAT) completed 3- Construction of target remote handling system 3- Online high power test of ISOL target (iThembaLabs) 4- Beam transport study with error analysis (CB to expTarget) 5- Upgrade cryogenic system (new controls) 6- Design of Cyclotron Control Access 6- Design of control system and EPICS implementation 6- Authorization request for UCx – Laramed operation (pending) | Bid for radioprotection surveillance Bid for control system network Bid for transport components (CB to end of ALPI) Bid for cryogenics upgrade Bid for vacuum system (CB-Alpi injection) Bid for additional bunkers doors Bid for Laser source | 1100 400 1500 800 1200 700 500
2014 Milestones and bids
(index refers to SPES components)
Funds: 6.800 kEuro

## Slide 53
Milestones | Main Bids | (k€)
1- Building and plants completed 2- Cyclotron: delivery, installation and SAT 3- Commissioning of target remote handling system 4- Commissioning of diagnostic box prototype 5- Charge Breeder installed 5- RFQ engineering design completed 6- Installation of access control system 6- Commissioning of Radioprotection surveillance | Bid for ISOL laboratory and hot cell Bid for transport system (BC, 1+line, MRMS-platform, diagnostic) Bid for RFQ materials and RF System Bid for access control system Bid for Safety System Bid for control of RF, diag, transp Partial payment of building | 2900 1500 1900 600 1200 1500 1000
2015 Milestones and bids
(index refers to SPES components)
Funds 11.900 kEuro

## Slide 54
SPES organization
Steering Committee
INFN
MAC
TAC
SAC
Scientific Advisory Committee
Gilles de France (GANIL), B.Fornal (Kracow),
P.Van Duppen (Leuven-Rex-Isolde),
T. Motobayashi (RIKEN), K.Gelbke, (FRIB)
T.Aumann (Darmstadt),
A.Vittuti, A.Olmi
ex-officio:
G. deAngelis, G.Cuttone, G.Fiorentini, G.Prete
Y. Blumenfeld (IPN-Orsay),
L.Miralles (CERN),
R. Ferdinand (GANIL),
D. Rifuggiato (LNS),
R. Catherall (ISOLDE),
M. Pelliccioni (INFN),
P. Fabbricatore (INFN-Ge)
Technical Advisory Committee
SPES Project Leader
Management
Board (WP Leaders and Deputies)
Project Work Packages and Work Units
Scientific working group
Scientific coordinator
INFN nuclear physics community
Steering Committee:
Giovanni LaRana, (Sez. Napoli)
Mauro Bruno (Sez. Bologna)
Sara Pirrone (Sez. Catania)
Adriana Nannini (Sez. Firenze)
Franco Camera (Sez. Milano)
Dino Bazzacco (Sez. Padova)
Lorenzo Corradi (LNL)
Titti Agodi (LNS)
Luigi Cosentino (LNS)
˜ as in TAC1: MB better defined; 1 replacement in TAC

## Slide 55: SPES Project Organization

## Slide 56: Project Structure

## Slide 57: Alignment between LNL structure and Project structure
The high level structure of the project and the WP structure bears some alignment
with the LNL structure, which is deemed to be more efficient than a pure matrix,
given the rather limited number of units involved.

## Slide 58
 | compertenze | Formazione | TD
1 | Sicurezze e radioprotezione | 1 | 2
2 | Controlli EPICS e di sicurezza | 5 | 1
3 | Sviluppo bersagli UCx | 1 | 
4 | Sorgente ISOL | 1 | 1
5 | LASER per ionizzazione |  | 1
6 | Charge Breeder e ECR | 1 | 1
7 | Beam Cooler e separazione in massa | 2 | 
8 | Impianti vuoto e recupero gas |  | 1
9 | Handling bersaglio | 2 | 
10 | Ciclotrone | 1 | 1
11 | Infrastrutture | 1 | 
12 | Progettazione Meccanica | 3 | 
13 | Meccanica | 2 | 
 | Altri (TapeSystem) | 1 | 
 |  | 21 | 8
anno | keuro
2015 | 430
2016 | 252
2017 | 117
2018 | 138
Personale in formazione (Borse e Assegni)
Fondi Direttore LNL
COSTI personale formazione (k€):
Personale in formazione e a Tempo Determinato per la realizzazione del progetto
Piano del direttore per il personale a Tempo Determinato da mantenere su fondi esterni fino al 2018

## Slide 59: High Power SPES Target (70 MeV)
 | Proton Energy | Proton current | UCx target | Target power | In-target Fission/s
SPES | 40 MeV | 0.2 mA | 30 gr | 8 kW | 10E13 f/s
Up-grade under study | 70 MeV | 0.15 mA | 60 gr | 10 kW | 2x10E13 f/s
Up-grade to be evaluated | 70 MeV | 0.3 mA | 60 gr | 20 kW | 4x10E13 f/s
dump
target
Chart: integral of Fission for a 70 MeV protons on UCx according to the number of disks
300 µA | 3402675000000 | 6802110000000 | 10195485000000 | 13580370000000 | 16947495000000 | 20283375000000 | 23568450000000 | 26781840000000 | 29880870000000 | 32836785000000 | 35631270000000 | 38234415000000 | 40678260000000
200 µA | 2268450000000 | 4534740000000 | 6796990000000 | 9053580000000 | 11298330000000 | 13522250000000 | 15712300000000 | 17854560000000 | 19920580000000 | 21891190000000 | 23754180000000 | 25489610000000 | 27118840000000
150 µA | 1701337500000 | 3401055000000 | 5097742500000 | 6790185000000 | 8473747500000 | 10141687500000 | 11784225000000 | 13390920000000 | 14940435000000 | 16418392500000 | 17815635000000 | 19117207500000 | 20339130000000
Disk: 0,9 mm
UCx density: 4,2 g/cm2

## Slide 60: Energy of SPES Post-Accelerator as function of A/q
Preliminary results for ALPI upgraded performances
Low Beta=5 MV/m, Medium Beta=5.5 MV/m, High Beta=5.5 MV/m
Low Beta=5 MV/m, Medium Beta=4.3 MV/m, High Beta=5.5 MV/m
EBIS charge state
ECRIS charge state
132Sn 27+
132Sn 21+
Actual SPES
Upgraded SPES
(2 cavities as margin)

## Slide 61: LARAMED Products
Radioisotope | Half-life
Fe-52 | 8.3 h
Cu-64 | 12.7 h
Cu-67 | 2.58 d
Sr-82 | 25.4 d
Ge-68 | 270.8 d
I-124 | 4.18 d
Ac-225 | 10 d
Some radionuclides of interest for nuclear medicine. They can be produced by means of the cyclotron of the SPES-a phase

## Slide 62
In the last few years a new radiopharmaceutical has been developed, labelled with Cu‐64 e Cu‐67, that selectively concentrates in hypoxic cells
The new molecule ([64/67Cu]ATSM ) has proved to be particularly useful in diagnosys and therapy of prostatic neoplasies, where the tracer [18F]FDG cannot be used.
A cyclotron of medium-high energy is an effective tool to increase the production yields of Cu‐64 and, consequently, enhance the availability of [64Cu]ATSM
[64/67Cu]ATSM
Isotope | Cu-64 | Cu-67
t 1/2 | 12.7h | 2.5d
EC | 41% | -
b+ | 19% | -
b- | 39% | 100%
64Cu and 67Cu

## Slide 63: 68Ge/68Ga
Together with F‐18 e C‐11, recently, the request of the β+ emitter radionuclide 68Ga has grown exponentially.
This interest is based on the fact that Ga‐68 proved to be
Isotope | Ge-68 | Ga-68
t 1/2 | 271d | 68m
EC | - | -
b+ | - | 100%
b- | 100% in Ga-68 | -
very useful being stably labeled to small peptidic biomolecules , used in the diagnosys of many pathologies of peptide receptor tissues.
The production, by means of medium-high energy cyclotrons, will provide an effective solution to the problem of availability of the generator nuclide 68Ge, whose production, with the methods used nowadays, is insufficient.

## Slide 64: 82Sr/82Rb
This radioisotope is actually produced in low energy cyclotrons, that do not allow high yields due to low energy and intensities .
Isotope | Sr-82 | Rb-82
t 1/2 | 25d | 1.27m
EC | 100% in Rb82 | -
b+ | - | 100%
b- | - | -
The ion Rb+ is a biologic analog of K+, fundamental in the heart cell operation.
Once administered by intravenous injection, Rb+ is assembled in the myocardium and, when sustituted with a g emitter radioisotope, it can be use as tracer to study the cardiac operation.