## Slide 1: European XFEL @ INFN Milano - LASA Daniele Sertore
Consiglio di Sezione, 12 giugno 2015

## Slide 2: The European XFEL
Some specifications
Photon energy 0.24-24 keV
Pulse duration ~ 10-100 fs
Pulse energy few mJ
Superconducting linac. 17.5 GeV
10 Hz (27 000 b/s)
5 beamlines / 10 instruments
  Start version with 3 beamlines and 6 instruments
Several extensions possible:
  More undulators
  More instruments
  …….
  Self Seeding
  CW Operation
SASE2
(= SASE1)
SASE1, lu= 40 mm
0.2 – 0.05 nm
17.5 GeV
SASE3, lu= 68 mm
1.7 – 0.4 nm

## Slide 3
Status of EXFEL installation
http://www.xfel.eu/
SC Linac
Undulators and Photon Beamline
EXFEL Injector
Experimental Hall

## Slide 4: Timeplan from the project general schedule
WHEN | MILESTONE
1st September 2015 | RF Gun Conditioning
31 October 2015 | Injector Tunnel closed
31 January 2016 | SASE1 experimental area ready for instrument (FXE, SPB/SFX) installation
31 May 2016 | SASE3 experimental are ready for instrument (SCS, SQS) installation
30 June 2016 | Linac tunnel closed
31 December 2016 | First SASE1 lasing possible
30 April 2017 | SASE1 instruments begin operation

## Slide 5: Impegno Italiano: 33 M€ (2005) in-kind
Contributo alla fase di costruzione di XFEL
    In-kind, per un valore di 33 M€ (indicizzato 2005) secondo le cifre indicate a “budget book” e approvate insieme alla Convenzione. Comprende:
        attività di sviluppo.
        Attività di trasferimento di know-how.
        Attività di produzione con l’industria, di collaudo e certificazione.
Attraverso la partecipazione responsabile dell’INFN, l’Italia garantisce la fornitura di
    Parte dei criomoduli
    Metà delle cavità superconduttive a 1.3 GHZ
    Controllo dell’istallazione degli apparati di sintonia
    Sistema completo di terza armonica (cavità e criomodulo)

## Slide 6: Contributi «Tecnici» di Milano nei WP
Riconosciuti nella struttura di progetto
WP3 Cryomodule (concluso)
WP4 Cavities
  WPL P.Michelato
WP7 Tuners
  WPL A.Bosotti
WP46
  WPL P. Pierini

## Slide 7: WP4: SC Cavities (1.3 GHz)

## Slide 8: WP4: Task
  800 cavità superconduttive da produrre in 2 aziende (50% ognuna):
  Ettore Zanon (EZ)
  RI Research Instruments (RI)
Produzione organizzata come «built to print»: specifiche dettagliate di costruzione che comprendono anche la descrizione dell’infrastruttura da utilizzare
Attività:
  Trasferimento tecnologico alle aziende EZ e RI (OK)
  Sviluppo e qualifica delle infrastrutture presso le aziende (OK)
  Qualifica componenti secondo normativa europea componenti in pressione EC/23/97(OK)
  Supervisione e controllo qualità durante la produzione (OK)
  Produzione in serie

## Slide 9: WP4: Status (updated 11-Jun-15)
Stato produzione delle 800 cavità (EZ + RI)
  Produzione «meccanica»: EZ (100%), RI (90%)
  Cavità spedite a DESY: 716
  Cavità testate a DESY: ~680
  Cavità spedite a Saclay per assemblaggio criomodulo: ~480
  Cavità accettate all’arrivo: ~70% (XFEL goal: 23.6 MV/m, Q0 1.1010)
    molti difetti recuperati con ritrattamento (HPR) a DESY
    dopo ritrattamenti > 90% cavità accettate
  Rate di produzione: 8 cav/settimana

## Slide 10: WP4: Cavities recovered with retreatment (HPR)
Average maximum gradient:
Before retreatment: 31.4 ± 6.9 [MV/m]
After retreatments: 33.6 ± 4.2 [MV/m]
Average usable gradient:
Before retreatment: 27.6 ± 7.1 [MV/m] After retreatments: 30.4 ± 4.5 [MV/m]
Max Accelerating Gradient
Usable Gradient (Eacc > 23.6 MV/m, Q0 > 1 1010)

## Slide 11: WP4: Cavity delivery rate (updated Jan-2015)
fsdfafff
8 cavities per week

## Slide 12: WP7: Tasks
Mechanics
Drive Unit
Piezo System
Preparazione della documentazione per la PRR (OK)
Scrittura delle specifiche per la richiesta di offerte alle ditte (meccanica, piezos, driver)(OK)
Preparazione delle istruzioni per l’assemblaggio in scala industriale (CEA) e istruzione personale (Alsyom) (OK)
Controllo qualità in fase di installazione presso CEA
Inoltre
Tuners coassiali per cavità 3H
R&D piezoelettrici
Cavità 3H con tuner coassiale
Studio, realizzazione e installazione dispositivo di sintonia statica e dinamica per cavità XFEL

## Slide 13: WP7: Installation quality control for piezotuners at CEA-Saclay(F)
Sistema completamente automatizzato: controllo di non conformità attraverso controlli funzionali incrociati
Controllo per ognuna delle tre fasi dell’assemblaggio del criomodulo
Report generato dopo ogni controllo e invito a EDMS – Check INFN sui report
101 criomoduli X 8 cavità - 45 criomoduli accettati a DESY
Personale CEA istruito da INFN

## Slide 14: WP46: 3rd Harmonic System (3.9 GHz)

## Slide 15: WP46: Tasks
Split between INFN-DESY (48%-52%) in-kind contributions
  INFN
    Design/procure (OK)
      Cavities (PED compliant)
      Tuners
      Cryomodule
    Vertical testing @ LASA (OK)
    Join assembly/test @ DESY (up to commissioning)
  DESY
    Procurement of quad/couplers/power RF and controls
      and “standard” 1.3 GHz components...
    Power RF testing (horizontal/module test) @ DESY jointly with INFN
    Most infrastructural work for module assembly/testing and installation (besides VT)
PED CERTIFICATION

## Slide 16: WP46: Series cavities Vertical Test
First cavity vertical test 26-Sep-14 and last 11-Feb-2015 Q>2 109, Max Eacc 19 MV/m
All 10 cavities above specifications!

## Slide 17: WP46: 3HZ010 Horizontal Test
SYSTEM QUALIFICATION of complete cavity package:
Nominal cold tuner range
Nominal QL
Nominal HOM behavior
Specs achieved
Probe | Quality Factor | VT | HT
Pick Up | Qt | 1.3 1010 | 1.5 1010
Hom MC Side | QHOM1 | 8.8 1013 | 2.2 1013
Hom PU Side | QHOM2 | 2.5 1012 | 1.5 1013
Long operation at 20 MV/m, stable
Cavity quenches at ~24 MV/m (~ 21 MV/m in VT)
Fixed coupler design
QL = 4.3 106
In range of final tuning with 3 stub tuner

## Slide 18: WP46: towards assembled cryomodule Status at 11 June 2015
Test Intercavity bellow connection
DESY task
Preliminary assembling of frequency tuner and magnetic shields
INFN Task
Waiting in CR for last two couplers and final string connections

## Slide 19: 2015-2016 Activities
WP4
  Expected end of cavity production Oct ‘15
WP7
  Expected end of module assembly Spring ‘16
    Support to CEA for piezotuner quality control
WP46
  Assembly cryomodule by August ’15
    CoolDown of XFEL Injector by Oct. ‘15
  Spare cryomodule in progress
    Cold Mass and Vacuum Vessel nearly ready
    10 spare cavities
      Ready by Fall ‘15
      VT Tested by Spring ’16
      Module Assembly Summer ‘16

## Slide 20: Photocathode Systems
The photocathodes for the EXFEL PhotoInjector are prepared by DESY using a production and trasport systems developed by INFN Milano.
INFN built and commissioned at DESY
  Additional Transport box
  Preparation system
INFN personel succesfully trained people at DESY to prepare cathodes.
System is routinelly working and, at present, assisting FLASH and PITZ RF Guns.

## Slide 21: Anagrafica XFEL per 2016
Ricercatori | Tecnologi | Ass Ricerca | Tecnici
Michelato | Bosotti | Bertucci | Bonezzi
Pagani | Monaco | Chen | Chiodini
Pierini | Paparella | + Ass. Ric. | Fusetti
Sertore |  |  |