## Slide 1
Diagnostics for XPR
CNAO BD Group
Pavia, 15 July 2015
Notes: 1

## Slide 2: BD Shopping List
Consequently to the proposal to make the Channeltron detector available for the XPR line, the ‘BD shopping list’ has been changed as follows:
  3 SFP profile monitors (equipped with IN/OUT actuator and tank: 2 for the XPR line and 1 to replace H2025SFH when Channeltron is installed);
  1 QPP, namely an SFP to be used as qualification profile monitor (equipped with IN/OUT actuator and tank) [note: SFP and QPP mechanics is very similar and we are evaluating the possibility to build exactly the same mechanics for both the purposes];
  (suppressed to save money (10keuro): the spare SFP, with no tank and no actuator. It means no detector for isocenter measurements [are we sure about this economy?]);
  1 Channeltron Fast Intensity Monitor to be installed in H2025, namely before the XPR line forks from the HEBT line [still to be approved in the budget].
Pag. 2
9/set/2014
Diagnostica per la linea sperimentale

## Slide 3: Time Schedule /1
SFP / QPP:
  Fibers are metalized and validated by CNAO people from some months; they are at AXE (France) waiting for the shipment. We have just discovered that INFN cannot pay the shipment (?) and now we shall find the money to pay it;
  When we have the fiber at CNAO, we can contact the (Italian) firm designated to assembly the fibers and make the mechanics. Estimated construction time is 2 months from the order [to be honest we are not contacting the firm from many months because of the project ‘pause’ and we are not presently updated about the firm amount of job in the next months. It’s difficult keeping a good contact with firms in this scenario…];
  Since fibers are still in France and July/ August is holiday time, we cannot hope to launch to order before mid-September. Namely, SFP and QPP could be ready by end of the year if there are no new obstacles.
  In which way can P.Poilleux expertise be paid?
Pag. 3
9/set/2014
Diagnostica per la linea sperimentale

## Slide 4: Time Schedule /2
Channeltron:
  Premise:
    Channeltron construction has not been offiacially approved yet in the budget;
    Channeltron estimated construction time is 2 months from the order;
    It is mandatory that the Channeltron tank be installed at H2025 at the time the experimental line is installed, being a major intervention in term of installation and alignment of the rest of the line. On the other hand, the Channeltron itself can be easily installed on tank later (note: very likely the line optics needs to be revised after its installation);
  From this premise and from the fact the first Channeltron is planned to be installed (at H4018FIM) along the therapeutic HEBT line next October 2015, we propose to build and install the tank soon, while waiting few months before launching the second Channeltron construction, so to have time to update the design with the eventual needs resulting from the first commissioning measurements (Could we plan to start the construction in Spring 2016?)
Pag. 4
15/jul/2015
Diagnostica per la linea sperimentale

## Slide 5: Conclusions
  BD time schedule is not late but strongly dependent on the XPR project responsiveness:
  When can we ship to CNAO metalized fibers?
  When can we contact firms to start SFP/ QPP construction?
  Is the Channeltron construction approved or not? When can we have this answer?
  When will the CNAO-UniBg contract be defined? [CNAO needs UniBg manpower and expertise to finalize SFP electronics]
Pag. 5
15/jul/2015
Diagnostica per la linea sperimentale