## Slide 1: Fondamenti di Project Management E PIANIFICAZIONE OPERAZIONALE PER la Gestione DI PROGETTI DI RICERCA
Luisella Lari
llari@cern.ch
Corso di Formazione INFN inter-struttura:
Sezioni di Bologna, Ferrara, LNGS, Perugia e Pisa.
6-7 June 2013 - Hotel Giò, Perugia

## Slide 2: Lecture 2 PM for Scientific Project
Outlook
Scientific Projects: why are they different for PM?
Scientific vs. Research Projects
Parallel with Industrial Practices
Key topics for managing successfully Scientific Projects:
  Industrial collaborations
  Experts reviews
  Project Management Plan
PM Standards vs. PM Methodologies

## Slide 3: Scientific Projects: why are they different for PM? (1/3)
Scientific Projects have an impact that can go well beyond the immediate completion of the project!
This indicates that the iron triangle is an indicator of project performance but not the best measure of project success.
Success is perceived not just by the traditional view of completing the work to time, cost and quality, but also by whether the project delivers the desired outcomes.
[See also: R. Turner et R. Zolin, Forecasting Success on Large Projects: Developing Reliable Scales to Predict Multiple Prospective by Multiple Stakeholders Over Multiple Time Frames, Project Management Journal (2012)
A. De Marco et C. Rafele, Program Management of the 2006 Olympic winter Games, Proc. PMI Global Congress, Edinburgh, Scotland (2005) ]

## Slide 4: Scientific Projects: why are they different for PM? (2/3)
Simplifying there are 3 disciplines needed for a successful Scientific Project:
Physics design;
Engineering design;
PM, as an integrating element to assure
on time, in budget and desired performance;

## Slide 5: Scientific Projects: why are they different for PM? (3/3)
So, everyone in the team has to understand the spirit and method involved in PM to e an effective contributor, no matter what your specially and position.
Cost of typical mistakes:
by Physicist/Engineer: ~ $10-100k,
by Manager: ~ $100k-Few Millions, even the Whole Project
Cost of PM generally less than 10% of the Scientific Project

## Slide 6: Scientific vs. Research Projects (1/3)
Scientific Project
Scientific project relies on the application of the scientific/systematic method.
LHC is a scientific project.
The Project Management discipline is applied to Scientific Projects.
Research Project
Research project is formal work which is undertaken systematically to increase the stock of knowledge.
PhD work is a research project.
No PM application  Outcomes of a research effort often lack a precise definition.

## Slide 7: Scientific vs. Research Projects (2/3)
Scientific Project

## Slide 8: Scientific vs. Research Projects (3/3)
Research Project
Research strategy for the Million Micro-ecosystem Genomes Project

## Slide 9: Parallel with Industrial Practices (2/2)
Scientific Project
Limited Component Prototype and is the Only and first System.
Higher risks in Technology and System Integration.
Difficulty in Personnel Transfer or Termination.
Flexible Reward Allowed.
Industrial Project
Component and System Demonstration before Mass Production.
Higher risks in Marketing, less in Technology.
Flexible Transfer and Termination.
Structure Reward Practice.

## Slide 10: Parallel with Industrial Practices (2/2)
Scientific Project
Focus on Prototype projects.
Specified Performance.
Controlled Schedule.
Close-loop Control.
Large and Diverse Groups.
Proactive.
R&D Project
Focus on sub-system.
Flexible Performance.
Flexible Schedule.
Open-loop Control.
Small and Familiar Groups.
Reactive.

## Slide 11: Example of Technical Incertitude
FNAL Main Ring Magnet Coil (6 versions), 1972.
NSLS RF Window, 1982.
ESRF Floor Movement, 1995.
KKB Electron Cloud, 2000.
J-PARC RFQ Vacuum and MR e-Cloud, 2009.
LHC SC high resistance cable joint, quench protection and vacuum interlock failure, 2008.
Accelerator
Projects

## Slide 12: Example of Performance Incertitude
SLAC/SLC, Reliability & Luminosity, 1983.
SSC, Cost Overrun, 1994.
LANL/PSR, Limited by e-Cloud, 2001.
FNAL/Tev-II, Delayed Performance, 2002.
CERN/LHC, Cost Increase of ~30%, 2002.
BP Gulf Oil Platform Explosion, Failure of Emergency Interlock, 2010.
Foxconn Incidents, Management/Culture approach, 2010.
Accelerator
Projects

## Slide 13: Key topics for Scientific Projects
Highlight on particular key topics to manage successfully complex Scientific Projects:
  The industrial collaborations or the Role of the Procurement.
  The experts reviews or the Role of Transfer Knowledge and Lessons Learned.
  The Project Management Plan or the “Rule of the Game”.

## Slide 14: Industrial collaborations (1/5)
Scientific Projects have generally a close relationship with Industry. Why?
Tighter budget in the Laboratories.
Better Equipped to perform Mass Production with high quality.
Standard Product with superior Performance (i.e. computers, klystrons, electronics, etc. ).
Easy of Manpower build-up and down.
Servicing and Upgrade.

## Slide 15: Industrial collaborations (2/5)
How Scientific Projects can success with Industrial collaborations?
Start Design and Final Specification Early.
Rule of Selecting the Lower Bidder:
  Familiarize with Vendors Market
  Pre-qualifications
  Site Inspections
Create Leverage Over Vendors by Introducing Incentive and Penalty Clauses.
Follow Development of the Manufacturing Work at Plant by Constant Contact and Frequent Site visits.

## Slide 16: Industrial collaborations (3/5)

## Slide 17: Industrial collaborations (4/5)
Silicon pixel detector (80M channels)
Silicon strip detector (~100 m2 of silicon micro strips )
Diamond pixel/strip detectors
Gas straw detector using transition radiation effect (300000 straws)
Liquid Argon electromagnetic sampling calorimeter (300 tons)
Scintillating Tiles calorimeters (42 tons of scintillator, 1100 km of readout fibers)
Scintillating fibers techniques
Cerencov counters
Large area gas drift chambers for muon detection (precision and trigger)
Radiation hard nsec electronics, mostly digital
Analog and Digital pipeline
Optical fibers readouts and transmission
Superconductivity and cryogenics
Complex mechanical structures analysis, seismic analysis, composite materials
Ultra vacuum techniques
Detectors, cables and electronics cooling
Large scale connectivity, DC-DC power converters technologies, HV technologies
PVSS slow control architecture
Scalar data acquisition and multilevel trigger systems, large computing farms
GRID environment
Fancy (spectacular !) transports and logistics
ATLAS detector
A Project of about 550 M$ in industrial collaboration!

## Slide 18: Industrial collaborations (5/5)

## Slide 19: Experts review (1/3)
Scientific Projects need several experts reviews during the several project life-cycles. For what?
evaluation of research and innovation proposals;
monitoring the progress, outcome and impact of research and innovation programs as well as giving advice on the shape of future activities;
motivating the project team to progress in the project in order to reach the project milestones;
encouraging exchanges;
facilitating consensus;

## Slide 20: Experts review (2/3)
Example RHIC Booster
~ 30 Million $ project, constructed in 1987-1990

## Slide 21: Experts review (3/3)
Example RHIC Booster

## Slide 22: Project Management Plan (1/7)
A Project Management Plan is an approved document, defining how the project is managed during its entire end-to-end life, covering all project phases, from initiation through planning, execution and closure.

## Slide 23: Project Management Plan (2/7)
It is a key project management documents!
It tells how to organize the project in a common framework.
Release a successfully project management plan depends by the size of the projects and from the project maturity level!

## Slide 24: Project Management Plan (3/7)
Complex Scientific Projects generally require the development of an articulate Project Management Plan.
It should include (as a minimum)

## Slide 25: Project Management Plan (4/7)
  Overview on the Project: including the purpose and objectives of the project, the key milestones and deliverables, dependency and constraints that may influence the the completion of the project.

## Slide 26: Project Management Plan (5/7)
  Project Organization: e.g. name of the Project Manager, key project team members and other project team member. For complex Research Project also the staff Organizational Structure.

## Slide 27: Project Management Plan (6/7)
  Project Management Processes: including i.e. Scope Management Plan, Time Management Plan, Resource Management Plan, Quality Management Plan, Communication Management Plan, Risk Management Plan, Contribution Management Plan.

## Slide 28: Project Management Plan (7/7)
Example: Particle Accelerator Project
Initialization
Plan
Close
Execute
Control
Scientific
Justification,
Feasibility
Study
Design,
Cost,
Schedule
Detailed Design,
Prototypes,
Cost,
Schedule,
Quality assurance/control
Organization and Staffing,
Engineering
Optimization,
Specification
Procurement,
Assembly and Testing,
Project Control
Installation,
Machine Performance,
Component validation,
Schedule application software,
Design validation
Physics run,
Upgrade

## Slide 29: PM Standards vs. PM Methodologies (1/3)
What is a Standard?
What is a Methodology?
What is the difference between Standard and Methodology?
A Standard is a collection of PM knowledge areas that are generally accepted as best practice.
A Methodology is a set of methods, processes and practices that are repeatedly carried out to deliver projects.
The key concept is that you repeat the same steps for every project you undertake, and by doing that, you will gain efficiencies in your approach.
Standards give you PM guidance, whereas methodologies give you practical PM processes for managing projects. Standards are not methodologies, and vice versa.

## Slide 30: PM Standards vs. PM Methodologies (2/3)
Major Standards in Project Management:
Project Management Body of Knowledge
International Project Management Association (IPMA) Competence Baseline (ICB)
……..
International Organization for Standardization ISO 21500:2013
NASA System Engineering Handbook (2010)

## Slide 31: PM Standards vs. PM Methodologies (2/3)
Major Methodologies in Project Management:
Project IN Controlled Environment version 2 or PRINCE2
HERMES
……..
PRojects integrating Sustainable Methods or PRiSM
Extreme Management (Agile)

## Slide 32: References & More
[See also: W.T. Weng, Project Management for Accelerator Construction, Seminars, IHEP, Beijing (2010);
Project Management Plan guidance, National shipbuilding Research Program;
Link of US conferences on management Large Scale / Research Projects
http://www.projectscience.org/ -> Ref for Different Presentations;
J. Fuster, Comparison of the EC’s Project Cycle Management/Logical Framework Approach with International PM Standards and Methodologies, Proc. PMI Global Congress (2006)]

## Slide 33: End – Lecture 2 PM for Research Project
Summary
Why the Research Project are different from Industrial Project
Research Project special topics
PM Standards vs. PM Methodologies

## Slide 34: End – Lecture 2 PM for Research Project
Reserve slides

## Slide 35: PM Standards vs. PM Methodologies (1/2)
Major Standards in Project Management (more details) :
Project Management Body of Knowledge (PMBOK Guide) is a book which presents a set of standards terminology and guidelines for PM. The American National Standard Institute (ANSI) which assigns standards in the USA, assigned it (ANSI/PMI 99-001-2008) the Institute of Electrical and Electronics Engineers assigned it IEEE 1490-2011 for project management to PMI guidelines.
International Project Management Association (IPMA) Competence Baseline (ICB) Guide. IPMA is a non-profit, Swiss-registered organization for the promotion of PM internationally. The association was started in 1965 in Vienna by a European group of managers, and initially established under the name International Management Systems Association (IMSA). In 1979 the association was renamed to International Project Management Association.
……..
International Organization for Standardization ISO 21500:2013, Guidelines for quality management in projects. It is not a guide to PM itself. Guidance on quality in project management processes is discussed in this International Standard.
NASA System Engineering Handbook (2010). Top-level Guidance for good NASA system engineering practice, including project management. First publication in 1995.

## Slide 36: PM Standards vs. PM Methodologies (2/2)
Major Methodologies in Project Management (more details):
Project IN Controlled Environment version 2 or PRINCE2 is a project management methodology. It was developed by the UK government agency Office of Government Commerce (OGC) and is used extensively within the UK government as the de facto project management standard for its public projects. PRINCE2 was released in 1996 as a generic project management method.
HERMES was born as a software development methodology, originally based upon the German V-Model. HERMES is results oriented and provides additional views about roles and procedure. Following British and German government examples, HERMES was developed by the Swiss Government as its own Project Management Method. As a project phase based guidance method, HERMES existed since 1975 (with extensive revisions in the years 1986 and 1995) in public administration in Switzerland and in numerous enterprises.
……..
PRojects integrating Sustainable Methods or PRiSM is a structured project management method developed by GPM Global to align organizational sustainability initiatives with project delivery. GPM is a global reach accreditation body for the certification of Sustainability in Project Management (SiPM). This method of project management incorporates the ideology of People, Planet, and Profit in regard to the Process & Product(P5) within project management.
Agile management is an iterative method of determining requirements for engineering and information technology development projects in a highly flexible and interactive manner. Agile techniques may also be called Extreme Project Management. It is a variant of Iterative life-cycle where deliverables are submitted in stages (The basic idea behind this method is to develop a system through repeated cycles (iterative) and in smaller portions at a time (incremental). At each iteration, design modifications are made and new functional capabilities are added.). One difference between agile and iterative development is that the delivery time in agile is in weeks rather than months. Both iterative and Agile methodologies were developed as a reaction to various obstacles that developed in more traditional project management. For example, as technology projects grow in complexity, end users tend to have difficulty defining the long term requirements, without being able to view progressive prototypes.