## Slide 1: Fondamenti di Project Management E PIANIFICAZIONE OPERAZIONALE PER la Gestione DI PROGETTI DI RICERCA
Luisella Lari
llari@cern.ch
Corso di Formazione INFN inter-struttura:
Sezioni di Bologna, Ferrara, LNGS, Perugia e Pisa.
6-7 June 2013 - Hotel Giò, Perugia

## Slide 2: Lecture 6 Controlling Projects
Outlook
Quality control
How to measure project performance?
The EVM method
Status Reports
Software packages

## Slide 3: Basic project life-cycle
Research Projects like any other project can be summarize in the 5 process groups.
Initialization
Plan
Close
Execute
Control
Creative
phase
Rigorous
phase

## Slide 4: Basic Project Documentation (1/2)
Initialization
Plan
Close
Execute
Control
Front-End
Project
Close-out
CDR
Proposal
Roadmap
TDR
+ Plan
Report
Report
Report
Report
…..
Lesson Learn

## Slide 5: Basic Project Documentation (2/2)
The NASA Program/Project Life-Cycle
Mission Req. definition
Design Development
Preliminary Design Review
Design Requirements
Baseline
Established
Critical
Design Review
Drawing
Baseline
Established
First Article Configuration Inspections
Manufacturing
Product
Baseline
Established
Verification of
manufacturing vs. design specification and assessment of the test results
Test and checkout
Costumer Acceptance Review
1 2 ….. n
Delivery
Design Certification Review
Launch
Certify flight and ground systems for manned flight
Operations
Flight
Readiness
Review
Det. Flight readiness
of spacecraft and release for launch

## Slide 6: Monitoring the project (1/2)
Monitoring the status of the project is necessary
to update project progress and to manage changes.

## Slide 7: Monitoring the project (2/2)
Monitoring includes:
Status Reporting
Progress Measurement
Forecasting
Report

## Slide 8: Quality Control
Quality Management  includes the Quality Plan,
Perform Quality Control and Perform Quality Assurance
How?
Audit the results of Quality Control
Collect results of executing Quality activities
[See also: J. E. Diekmann, Quality Control – The key Element in Project Control, Project Management Quarterly (1981)]

## Slide 9: Quality Control Charts

## Slide 10: Cause and Effect Diagrams (1/2)
Ishikawa Diagrams or Fishbone Diagrams
Effect
Causes

## Slide 11: Cause and Effect Diagrams (2/2)
Ishikawa Diagrams or Fishbone Diagrams
Effect
Causes

## Slide 12: Pareto Histogram
Pareto law: 80% of the problems
are due to 20% of the cause
Causes
Frequency

## Slide 13: Quality control…more
There are more Quality Control analysis methods…..the idea is to collect data to evaluate the Cost of Quality

## Slide 14: How to measure project performance?
Earned Value Management (EVM) is the a commonly used method of performance measurement.
EVM integrates project scope, cost and schedule measures.

## Slide 15: EVM Method (1/5)
S-curve
S-curves are an important project management tool. They allow the progress of a project to be tracked visually over time, and form a historical record of what has happened to date.

## Slide 16: EVM Method (1/11)
Steps to create the Baseline S-curve…
End Point
Start Point
Considering all the Project Activity
I know when I pay!

## Slide 17: EVM Method (2/11)
Baseline S-curve
Planned Value (PV)
Budget At Completion (BAC)

## Slide 18: EVM Method (3/11)
Actual Cost (AC) of work performed
“costo sostenuto alla data corrente tR”

## Slide 19: EVM Method (4/11)
Earned Value (EV) of work performed
“costo delle attivita’ realizzate alla data corrente tR”

## Slide 20: EVM Method (5/11)
Why EVM is an integrated method?
Schedule Variance (SV)
Variance Index

## Slide 21: EVM Method (6/11)
Why EVM is an integrated method?
Cost Variance (CV)
Variance Index

## Slide 22: EVM Method (7/11)
Performance Index  how close the project is to the cost/schedule baselines the work performed
Critical Ratio (CR)
Cost Performance Index (CPI)
Schedule Performance Index (SPI)

## Slide 23: EVM Method (8/11)
Forecasting
Estimate At Completion (EAC)
 TYPICAL variance
 ATYPICAL variance
Estimate To Complete (ETC)
[See also: F. Caron, F. Ruggeri et A. Merli, A Bayesian Approach to Improve Estimate at Completion in Earned Value Management, Project Management Journal (2013)]

## Slide 24: EVM Method (9/11)
Exercise Lecture 6

## Slide 25: EVM Method (10/11)

## Slide 26: EVM Method (11/11)

## Slide 27: Status Reports (1/2)
Quality
EVM
Engineering Change Request
Update
Baselines
….etc.
At the right person 
the right information

## Slide 28: Status Reports (2/2)
At the right person 
the right information
Where I can find this information?
Communication Plan
Communication Matrix

## Slide 29: The role of software packages
Database to store data and Software Packages to analyze data are been/is being developed for supporting Project Management
For each Project
a lot of Data are produced !!
[See also: M. Ferrari, Case Study: Primavera High Quality Schedules for the ITER Fusion International Project, COLLABORATE12, F4E (2012)]

## Slide 30: End – Lecture 6 Controlling Projects
Summary
Cost of Quality
EVM method
Status Reporting & Communication
Software