## Slide 1: Elements of Project Management and operational planning, Applied to SCIENTIFIC projects: focus on Quality and Project Risks MANAGEMENT
National Institute for Nuclear Physics
Luisella Lari
Corso Nazionale di Formazione INFN
.
16-19 September 2014
Hotel Giò, Perugia, Italia

## Slide 2: Lecture 5 Costing and Resource Planning
Outlook
Cost and Resource assignment
Cost Baseline
Finalizing the schedule
Procurement plan
Risk analysis/plan

## Slide 3: Basic project life-cycle
Scientific Projects like any other project can be summarize in the 5 process groups.
Initialization
Plan
Close
Execute
Control
Creative
phase
Rigorous
phase

## Slide 4: Basic Project Documentation (1/2)
Initialization
Plan
Close
Execute
Control
Front-End
Project
Close-out
CDR
Proposal
Roadmap
TDR
+ Plan
Report
Report
Report
Report
…..
Lesson Learn

## Slide 5: Basic Project Documentation (2/2)
The NASA Program/Project Life-Cycle
Mission Req. definition
Design Development
Preliminary Design Review
Design Requirements
Baseline
Established
Critical
Design Review
Drawing
Baseline
Established
First Article Configuration Inspections
Manufacturing
Product
Baseline
Established
Verification of
manufacturing vs. design specification and assessment of the test results
Test and checkout
Costumer Acceptance Review
1 2 ….. n
Delivery
Design Certification Review
Launch
Certify flight and ground systems for manned flight
Operations
Flight
Readiness
Review
Det. Flight readiness
of spacecraft and release for launch

## Slide 6: The cost of the project (1/3)
In Lecture 4  the estimation of Activity Duration and the method to estimate Activity Resource Requirements
…. establish the COST of the Project

## Slide 7: The cost of the project (2/3)
The size of a Scientific Project is a DOMINANT factor that drives the variation of costs
The scale-effect model is based on the determination of the unit of production

## Slide 8: The cost of the project (3/3)
The scale-effect FORMULA refers to the relationship between the cost C of (for example) a facility of capacity P and the cost C0 of an equivalent facility of capacity P0
Example: the construction cost of a 130 MW (P0) energy amplifier has been estimated C0 = 500 M$, then the construction cost of a P-MW Energy Amplifier is given by
C = 500x(P/130)k,
where k is [0.7;0.85]

## Slide 9: Cost Estimating (1/2)
Main Methods to Estimating Activity Cost
Similarity to other estimations
Historical Data
Expert advice
Parametric estimation
3-Points Technique
Bottom-up Technique
Cost of Quality
It is a challenging  in particular for Scientific Project

## Slide 10: Cost Estimating (2/2)
Rolling up all the costs at activity level
The whole estimated Project Cost

## Slide 11: Determine Budget (1/5)
Determine Budget is the process of aggregating the estimated costs to establish a Cost Baseline
The Cost Baseline includes all the authorized budgets, but excludes management reserve
Month
Year
Week

## Slide 12: Project Management Plan
The Cost Baseline is included in the Project Management Plan
See Lecture 2

## Slide 13: Finalizing the Schedule (1/2)
Up to now
Activity of the projects defined and developed a schedule that meets the expected end date of the project and on-budget.
Considering availability
Do you can accomplished this schedule with the resource available?

## Slide 14: Finalizing the Schedule (2/2)
Resource Leveling is a schedule network analysis technique
Starting Point is the Critical Path
Check if the same resource is allocated at different activity at the same time.
If it is the case  Do Not touch the Critical Path but Play with the Float range available (i.e. use the window early start time ES – late start time LF) to redistribute the resources.
If you can not respect the end project date within the budget with the resource available  Re-plan  New Critical Path.
If 30% of the resources are co-locate in time  New Critical Path

## Slide 15: Procurement plan
Procurement plan include all the process necessary to purchase or acquire products, services, or results from outside the project team.
The Procurement Plan is included in the Project Management Plan.

## Slide 16: Risk analysis (1/3)
Project Risk is always
in the future.
Technical, Programmatic or External Risks are uncertain events or conditions that, if they occur, have effects on at least one project objective (i.e. scope, schedule, cost, quality, ..)

## Slide 17: Risk analysis (2/3)
Know Risks are those that have been identify and analyzed.
Risks Matrix

## Slide 18: Risk analysis/plan (3/3)
Risk analysis allows to Plan intervention/mitigation action
How project risk management will be structured and performed on the project is a part of the Project Management Plan.
[See also: H. Thamhain, Managing Risks in Complex Projects, Project Management Journal (2013)]

## Slide 19: Example

## Slide 20: End – Lecture 5 Costing and Resource Planning
Summary
Cost Baseline
Resource Leveling
Work Plan