## Slide 1: Elements of Project Management and operational planning, Applied to SCIENTIFIC projects: focus on Quality and Project Risks MANAGEMENT
National Institute for Nuclear Physics
Luisella Lari
Corso Nazionale di Formazione INFN
.
16-19 September 2014
Hotel Giò, Perugia, Italia

## Slide 2: Seminar LHC Main Ring Project
CERN: Lessons learned from the Large Hadron Collider (LHC) installation mega project
Acknowledge to Katy Foraz (LHC Planning section leader)

## Slide 3: The foundation of CERN
The CERN Convention, established in July 1953, was gradually ratified by the 12 founding Member States
Today: 20 Members states
Annual budget : ~625 M€
2250 staff (physicists, engineers, technicians, …)
~700 other paid personnel
Some 9’500 visiting scientists ( > half of the world's particle physicists)
They come from >500 universities representing 80 nationalities.

## Slide 4: What is LHC?
LHC : Large Hadron Collider
  7 TeV proton-proton accelerator collider
  A 27 km circumference collider
  4 main experiments
The largest scientific instrument in the world
ALICE
ATLAS
CMS
LHCb
From 50 to 175 m underground

## Slide 5: The accelerators chain

## Slide 6: The LHC Main Ring

## Slide 7: Key Factors
Time Horizon
  Multi-years
  Multi-phases
Chain of Command
  Multi-layers organization
  Matrix Structure
High‐degree of Specialization
  Subject Matter Expertise
  Cutting-Edge Technology
Dispersed Teams
  Virtual teams in multiple
  locations
  Outsourcing to other countries
LHC characteristics
Impact on the project
Coordination becomes crucial
As well as clear and transparent communication
Responsibilities have to be clear
Risks have to be properly analyzed

## Slide 8: Some numbers
Magnets  About 60 variety of magnets  Main Dipole(14.3 m long). A total of 1232 are installed.  Cost: ~ 0.5 million CHF each.
Power Converters  1700 different power converters or power supplies.
Cryogenics  LHC cryogenics need 40,000 leak-tight pipe junctions.
Vacuum  In the LHC LSSs 780 ion pumps.
Collimators  108 Collimators around the ring, of which 97 are precision movable devices.
….
Main components of the LHC accelerator

## Slide 9: Cost structure of the LHC Main Ring
industrial contracts: ~ 2 billion €

## Slide 10: Cost structure of the LHC Main Ring
90 main industrial contracts in the world

## Slide 11: Important Dates
84 Preliminary studies
90 R&D program launched
94 Project approved by CERN council
96-99 Industrialization of production of series
98 DUP and start of civil engineering
98-01 Signature of main contracts
01 Start of installation
05 Start of Magnets installation
06 First functional tests
08 First beam
Coordination
schedule
R&D

## Slide 12: Organization of the Project
… at the time of LHC installation
Project Management
Departments
Committees
External Collaboration
AB
AT
FI
SG
TS
Canada
Host States
India
Japan
Russia
USA
LEMIC
MARIC
LTC
ICC
Working groups / Sub-projects
Matrix structure
LHC INSTALLATION SCHEDULE

## Slide 13: LHC Schedule Requirements
To co-ordinate the project requires an overall view, which can only be achieved by collecting and summarizing detailed information, which in turn is possible only if the information is coherent across the whole project.
There is also a desire to maximize the freedom of the technical groups to organize and manage their work.

## Slide 14: The LHC PM Approach
The concept of “deliverables” was introduced.
Each WU contained information about work/hr/logistic.
WU timeframe maximum 3 months.
All WUs were directly supervised by a CERN staff.
The WU responsible was trigged to fill a written report and justify achievements and delays.
The report was sent to the project leader who accepts or rejects it.  Review each month.
The WUs were used to monitoring resources spent (EVM).
The WORK UNITS

## Slide 15: The LHC PM Approach
How the WU concept was integrated into
the planning and the monitoring of the
LHC installation works?
The WORK UNITS

## Slide 16: The LHC PM Approach
Multi level planning
Design schedule
Manufacturing schedule
16
Master Schedule
Installation schedule
Detailed schedule
Detailed schedule
Detailed schedule
Detailed schedule
@ WU level

## Slide 17: The LHC Schedule Methodology
1. Master Schedule
Review the strategic goals and major milestones of the project.
Used for communicating progress outside the project team

## Slide 18: The LHC Schedule Methodology
2. LHC Construction and installation Schedule (1/4)
From strategic to tactic.
Aim: implement and control the flow of installation.
Respect the main milestones of the master schedule.
Based on WBS and activities lists.
Linear schedule.
Essential for the project follow up.
3.3 BCHF
11.000 WU

## Slide 19: The LHC Schedule Methodology
2. LHC Construction and installation Schedule (2/4)
How was the schedule organized?
The multi-phases of LHC:
Civil Engineering phase
General services phase
Cryogenic phase
Machine phase
Hardware Commissioning Phase
Installation
Studies & Integration

## Slide 20: The LHC Schedule Methodology
2. LHC Construction and installation Schedule (3/4)
How was the schedule organized?
Planning type “Chemin de fer”
No margins
For Cryo & Machine phases: pilot sector

## Slide 21
2. LHC Construction and installation Schedule (4/4)

## Slide 22: The LHC Schedule Methodology
3. Detailed installation schedules (1/3)
Derives from details of the installation and the knowledge of each WU
The aim of these schedules was
to ensure the work to do was feasible within the time slot allocated.
to ensure that the resource to achieve every tasks were available.
Each sub-schedule faced to specific requirements of installation.
The level of details was chosen to maximize the freedom of the technical group to organize and manage their work.

## Slide 23: The LHC Schedule Methodology
3. Detailed installation schedules (2/3)
Example 1.
Transfer line installation planning.
Major constraint: assure the test with beam end 2004, before SPS shutdown
Radiation constraint for the proximity to the SPS accelerator
1 year

## Slide 24: The LHC Schedule Methodology
3. Detailed installation schedules (3/3)
Example 2.
Collimation installation planning.
Major constraint: assure a continuity of work for the external vacuum team
Resource allocation studies
2 years planning

## Slide 25: The LHC Schedule Control
1. Determination the current status of the project schedule
  Weekly meetings  to follow the advancement progress of every installation work and to identify potential problems, through feedback from the production sites and from the field.  @ WU level
  Monthly meetings  to have a global review of the installation and to check the homogeneity of the installation procedure on the different work sites.  @ Management level
Schedule comparison bar charts

## Slide 26: The LHC Schedule Control
2. Evaluation of the factors that create schedule changes (1/3)
  Minor changes  impact limited to a restricted area of the activities  Revision of the Detailed Installation Schedule
  Major changes  impact on the whole project Schedule Change Requests circulated through the groups and approved by the project leader  Schedule Change Order

## Slide 27: The LHC Schedule Control
2. Evaluation of the factors that create schedule changes (2/3)
middle2007
end
2006
end
2007
middle
2008
Prepared by 4
Planning Officers
Dynamic process

## Slide 28: The LHC Schedule Control
2. Evaluation of the factors that create schedule changes (2/3)
2002
2003
2004
2005
2006
2007
Civil engineering
General Services
Cryogenic line installation
Machine installation

## Slide 29: Civil Engineering Phase
98
99
00
01
02
03
04
05
06
07
08
Underground works ~240’000 m3
4 main contracts
Issues
  Geological issues
  Modification of the contracts’ envelop
  35h law in France
Impact on resources and schedules
  Long discussions
  Fixed costs mechanism

## Slide 30: General Services Phase
98
99
00
01
02
03
04
05
06
07
08
More than 4’500km of cabling + 160km of pipes
Issues:
  Logistic (cable drums)
  Some delays in the first sector
  Late requests from final users
  Mechanical problems underestimated with the water cooled cables
    CERN dedicated team set up to solve quickly the problem
  End of worksites: Non conformities the last 2%

## Slide 31: Cryogenic Phase
98
99
00
01
02
03
04
05
06
07
08
5 cryogenic islands installed/modified
A cryogenic line
  One contract
  Started in June 2003
  After several months, big technical and qualitative issues
  Worksites stopped in July 2004
  In order to progress, CERN took the decision to repair and re-install the faulty components delivered. (one entire sector + other components)
  Worksites restarted in November 2004
  Finished in December 2006

## Slide 32: Impact of Cryo Delay
98
99
00
01
02
03
04
05
06
07
08
Technically:
  Systematic cold test canceled
  No more pilot sector
Logistic:
  Superconducting magnets to be stored
  Transport of magnets in // worksites
Organization
  Sequence of sectors changed
  Time window dedicated to machine phase reduced
    Scope of contracts (already placed) changed: human resources, additional tooling
  Time window of hardware commissioning reduced by a factor
    additional resources

## Slide 33: SuperConducting Magnets Transport
98
99
00
01
02
03
04
05
06
07
08
95% lowered down through one pit
  Weight(34t)/ admissible load of crane
  Dimensions : lenght~17m
More than 1’700 superconducting magnets transported
  3 km/h max
Main issues
  Crossing of worksite in narrow areas
  Delay on availability on surface : 1 hour 1 day!!

## Slide 34: Interconnections of Magnets
98
99
00
01
02
03
04
05
06
07
08
Including:
  More than 1’900 interconnections:
    10’000 Soldering
    60’000 Ultrasonic welding
  Vacuum tests
  Electrical tests
Slow start: missing magnets, co-activities
Nominal progress rate during 3rd sector

## Slide 35: Main Problems of Magnets
98
99
00
01
02
03
04
05
06
07
08
Main problems / the bad series:
  End 2006: Several defects on the Inner Triplets magnets
    CERN set up a dedicated task force for the design analysis and the repair
     First sector cool-down without these magnets in order to gain experience
  September 2007: During a warm-up (to connect the Inner Triplets), several PIMs were broken
    Ingenious solution developed for diagnosis
  February 2008: Conceptual problem on the connection cryostat

## Slide 36: Hardware Commissioning Phase
98
99
00
01
02
03
04
05
06
07
08
Each system was individually tested, then
Powering tests of each sector – painful start, but debugging was essential, and systematic errors were corrected

## Slide 37: The LHC Schedule Control
3. LHC Communication system (1/3)
  Aim: assure clear and transparent communication of the current situation & of the tactics changes
  Minutes of the weekly and monthly meetings were archived and available in the LHC Engineering Database Management System (EDMS).
  Progress reports that followed each monthly Installation Follow-Up meeting were prepared by the planning coordinators and published once a month on the WEB home page of the LHC project.
  The General coordination schedule was available on the WEB home page of the LHC project.

## Slide 38: The LHC Schedule Control
3. LHC Communication system (2/3)
  Very long lifecycles and need for internal knowledge transfer.
CERN
EDMS
  Master Plan
  Specifications
  Presentations
  Meeting Minute
  Manufacturing data
  Tests & measures results
  Transport data
  Inventory
  Tests & measures results @delivery
  Planning
  Installation progress
  ECRs with distributed approval process
  Commissioning procedures
  Safety notice
  Corrective actions
  Maintenance estimation
  Dismantling regulations
  Procedures

## Slide 39: The LHC Schedule Control
3. LHC Communication system (3/3)
  EDMS system also helpful to documenting the quality of the installation works.
  [Example of some strong constraints: Components are in many cases not accessible
  once installed (like in satellites) and µm tolerances in an installation of several kilometers]
FULL TRACEABILITY

## Slide 40: Lesson Learned
Did it work?
  Yes! At least we got a realistic and always up-to-date picture of the installation works.
  Objective picture without intermediate management interpreting the status.
  All was WWW published to allow the internal and/or the external collaboration to check it.
  However the late implementation of the EVM system to monitor project performance has limited its expected results.

## Slide 41: Lesson Learned
How to improve the performances…
  Perform spatial integration studies before starting installation.
  Split the major contract on the critical path between at last 2 concurrent firms.
  Set-up internal “risk” teams in order to react quickly to technical problems.
  Set-up storage areas in key position, in order to easy logistics.
  Allocate contingency time for consolidation of each phase.
  Create individual and independent sub-projects, to improve the flexibility during the installation and commissioning.

## Slide 42: References
P. Bonnal, “CAN A DELIVERABLE-ORIENTED Project Management Approach be the Foundations for a LEAN APPROACH?”, Journal of Modern Project Management, 2013, Brazil.
P.Bonnal, J.DeJonghe “EVM 2.0 Lessons learned from the LHC Project Collaborative EVM System”, EVM World’09, 2009, Naples, Florida, USA.
K.Foraz et al. “Schedule evolution during the life-time of the LHC project”, EPAC06, 2006, Edinburgh, UK.
P.Bonnal, J.DeJonghe, J.Ferguson “A deliverable-oriented EVM system suited to a large-scale project” Project Manage. J. 37(1), 2006, pp. 67–80.
P.Bonnal, D.Gourc, A.P.Hameri, G.Lacoste, “A linear-discrete scheduling model for the resource-constrained project scheduling problem.” Constr. Manage. & Economics 23(8), 2005, pp. 797–814.
K.Foraz, H.Gaillard, L.Lari, S.Weisz “Scheduling the installation of the Large Hadron Collider”, EPAC04, 2004, Lucerne, Switzerland.
L.Lari et al. “Scheduling the installation of the LHC injection lines”, EPAC04, 2004, Lucerne, Switzerland
C.Hauviller, S.Weisz “Installation of a particle accelerator: from the theory to practice”, EPAC04, 2004, Lucerne, Switzerland.
P.Bonnal, J.DeJonghe “The use of a linear scheduling approach for optimizing the installation of the LHC.” at 3rd Project Science Workshop, 2003, Aspen, CO, USA.
P.Bonnal, M.Vitasse “Organization of the installation work of LHC and its experiments”, CERN LHC Project Document LHC-PM-MS-0005, 2003, Geneva, Switzerland.
R.Saban “L’installation du LHC – La coordination sur le terrain” CERN LHC Project Document LHC-PM-IP-003, 2003 Geneva, Switzerland.
P.Bonnal, O.Lindholm, “Logistic simulation of the transportation of cryo-magnets for the LHC Project”. LHC Project Note no. 298, 2002 CERN, Geneva, Switzerland.

## Slide 43: Seminar