## Slide 1: Elements of Project Management and operational planning, Applied to SCIENTIFIC projects: focus on Quality and Project Risks MANAGEMENT
National Institute for Nuclear Physics
Luisella Lari
Corso Nazionale di Formazione INFN
.
16-19 September 2014
Hotel Giò, Perugia, Italia

## Slide 2: Lecture 3 Project Initialization and Scoping
Outlook
An Overview on the project:
  Basic life–cycle project
  Basic Project Documentations
The Front-End phase
Project Scope
Scope Creep
Special topics:
  draft WBS of the Project
  Responsibility Matrix
  Risk identification

## Slide 3: Basic project life-cycle
Scientific Projects like any other project can be summarize in the 5 process groups.
Initialization
Plan
Close
Execute
Control
Creative
phase
Rigorous
phase

## Slide 4: Basic Project Documentation (1/2)
Initialization
Plan
Close
Execute
Control
Front-End
Project
Close-out
CDR
Proposal
Roadmap
TDR
+ Plan
Report
Report
Report
Report
…..
Lesson Learn

## Slide 5: Basic Project Documentation (2/2)
The NASA Program/Project Life-Cycle
Mission Req. definition
Design Development
Preliminary Design Review
Design Requirements
Baseline
Established
Critical
Design Review
Drawing
Baseline
Established
First Article Configuration Inspections
Manufacturing
Product
Baseline
Established
Verification of
manufacturing vs. design specification and assessment of the test results
Test and checkout
Costumer Acceptance Review
1 2 ….. n
Delivery
Design Certification Review
Launch
Certify flight and ground systems for manned flight
Operations
Flight
Readiness
Review
Det. Flight readiness
of spacecraft and release for launch

## Slide 6: Front-End phase (1/6)
Project Proposal is the basis of the project selection!
Project Managers may not be responsible of project selection, but they might participate in developing the project proposal!

## Slide 7: Front-End phase (2/6)
An approved Project Proposal announces that a new project has begun.
The purpose of it is to demonstrate management support for the project and the Project Manager.

## Slide 8: Front-End phase (3/6)
An approved Project Proposal is
powerful
but not necessary complex.
1+1=2

## Slide 9: Front-End phase (4/6)
1. The process begins with defying a need.
2. Sorting wants versus need.
3. Converting needs into requirements.
4. Identify straightforwardly all possible solutions.
5. Propose one solution and demonstrate its feasibility.

## Slide 10: Front-End phase (5/6)
Roadmap
Project Board or
Strategic/Steering
Board/Committee
Ensure the strategic management of the project;
Is ultimately responsible w.r.t. successful completion;
Guarantee the acquisition and availability of resources;
In case if conflicts, arbitrate;
Who?

## Slide 11: Front-End phase (6/6)
From Proposal to CDR  adding constraints to the project
Proposal
Roadmap
CDR
Exercise Lecture 3

## Slide 12: Proposal doc typical contents
1. Executive summary (to the attention of…)
2. Initial Situation (i.e. the problem statement)
3. Aim and objective of the proposed project
4. Possible solutions
5. A priori preferred solution
  Description
  Identification of the main Stakeholders
  Phase, organization, draft WBS/plan
  Resource required
  Outcomes and benefits
6. Major risks identification
Proposal

## Slide 13: Roadmap doc typical contents
1. To 6.  as Proposal
7. Decision or Project Pre-analysis
  Approval of the senior management
  Approval of the project organization
  Decision to go through with the preferred solution
  Decision to detail the draft plan
Roadmap
CDR doc typical contents
CDR
CDR is a technical oriented doc, while Project Proposal and Roadmap are Project Management docs.
CDR is developed to demonstrate the feasibility of the project.
[ See also: P. Bonnal, RéVE – Réservation des Vélos Électriques
Mandat de Projet (purement fictif), Creative commons (2011)]

## Slide 14: Project Scope (1/3)
Proposal
Roadmap
CDR
Note that the Project Scope is defined in the first doc and detailed in the following docs.
Project Scope is the work that must to be performed to deliver a product, service, or a result with the specified features and functions.

## Slide 15: Project Scope (2/3)
[Ref: F. Hooks, Don’t start the building without the Blueprint: Defining the Scope of a Project, Journal PMNetwork (1994)]
Civil architects understand that you need to architect the project before you begin.
All other large complex must perform this architecting process.
Example: the ISS scope crisis in ‘90.

## Slide 16: Project Scope (3/3)
Doran’s SMART characteristics provide a criteria for scope definition:
S for Specific  be specific in targeting objective.
M for Measurable  establish a measurable indicator(s) of progress.
A for Assignable  Make the object assignable to one person for competition.
R for Realistic  State what can realistically be done with available resources.
T for Time-related  State when the objective can be achieved (i.e. the duration).
[Ref: G. T. Doran, There's a S.M.A.R.T. way to write management's goals and objectives, Management Review, Volume 70, Issue 1, AMA FORUM (1981)]

## Slide 17: Scope Creep
This is the term used to describe the changes to the scope of a project that occur after the Project Scope has been approved.
[ See also: L. Sliger, Goodbye Scope Creep – Hello Agile!, Proc. PMI Global Congress (2010)]

## Slide 18: Special topics: draft WBS
Work Breakdown Structure (WBS), in PM is a deliverable oriented decomposition of a project into smaller components
(see Lecture 4 for details).
First appear of High level WBS and main project phases could in the Proposal doc.
i.e. the Level 0
Proposal

## Slide 19: Deliverables (1/2)
When a deliverable is an object, it is useful to split it into parts or components to obtain a bill-of-material called a Product Breakdown Structure (PBS).
Deliverables are not limited to hardware (e.g. product, facility, system). They could be also services (e.g. testing, licensing), support (administration), data (report, engineering data management system), or any other function/process.

## Slide 20: Deliverables (2/2)
Deliverables Process Integration
The PBS is a view of the project in terms of its physical components detailed at a level of manageable size.
Every deliverable identified in the PBS is associated with the process necessary to its realization (WBS).

## Slide 21: Special topics: Responsibility Matrix (1/2)
A Responsibility Assignment Matrix (RAM) describes the participation by various roles in completing tasks or deliverables for a project.

## Slide 22: Special topics: Responsibility Matrix (2/2)
A variation of the RAM is the RACI Matrix

## Slide 23: Special topics: Risks identification
Identifying Risks relevant to the project is a process could start within the Proposal doc.
Generally speaking it is more relevant for Industry!
Time To Market (TTM) is the length of time it takes from a product being conceived until its being available for sale.

## Slide 24: End – Lecture 3 Project Initialization and Scoping
Summary
The definition of top-level project objective
To commit the organization to a project or phase
The assign a Project Manager to the project