## Slide 1: Elements of Project Management and operational planning, Applied to SCIENTIFIC projects: focus on Quality and Project Risks MANAGEMENT
National Institute for Nuclear Physics
Luisella Lari
Corso Nazionale di Formazione INFN
.
16-19 September 2014
Hotel Giò, Perugia, Italia

## Slide 2: Lecture 4 Project Planning
Outlook
WBS
Critical Path Method
Precedence Diagramming Method
Linear Planning
Baseline schedule
Project Management Plan

## Slide 3: Basic project life-cycle
Scientific Projects like any other project can be summarize in the 5 process groups.
Initialization
Plan
Close
Execute
Control
Creative
phase
Rigorous
phase

## Slide 4: Basic Project Documentation (1/2)
Initialization
Plan
Close
Execute
Control
Front-End
Project
Close-out
CDR
Proposal
Roadmap
TDR
+ Plan
Report
Report
Report
Report
…..
Lesson Learn

## Slide 5: Basic Project Documentation (2/2)
The NASA Program/Project Life-Cycle
Mission Req. definition
Design Development
Preliminary Design Review
Design Requirements
Baseline
Established
Critical
Design Review
Drawing
Baseline
Established
First Article Configuration Inspections
Manufacturing
Product
Baseline
Established
Verification of
manufacturing vs. design specification and assessment of the test results
Test and checkout
Costumer Acceptance Review
1 2 ….. n
Delivery
Design Certification Review
Launch
Certify flight and ground systems for manned flight
Operations
Flight
Readiness
Review
Det. Flight readiness
of spacecraft and release for launch

## Slide 6: WBS (1/5)
Work Breakdown Structure (WBS), in PM is a deliverable oriented decomposition of a project into smaller components.
Work Package is the lower level in the WBS.
Activities/Tacks are the smaller components of work package.
Activities/Tacks provide a basis for estimating/scheduling/executing/monitoring and controlling the project

## Slide 7: WBS (2/5)
Example 1: Landscape Project
Chart form
2.1
Acquire lawn material
2.2
Install sprinkler system
2.3
Plant grass
2.4
Plant shrugs
3.1
Acquire fence material
3.2
Construct fence
2.2.1
Identify sprinkler locations
2.2.2
Dig trenches
2.2.3
Install pipe and hardware
2.2.4
Cover sprinkler system
2.3.1
Remove debris
2.3.2
Prepare soil
2.3.3
Plant lawn seed
3.2.4
Paint/stain fence
3.2.3
Install fencing and gates
3.2.2
Install posts
3.2.2
Mark fence line and posts
Landscape Project
2.0
Put in lawn
1.0
Design Home Landscape
3.0
Build fence

## Slide 8: WBS (3/5)
Example 1: Landscape Project
WBS in outline form
Home Landscape project
1.0 Design home landscape
2.0 Put in lawn
2.1 Acquire lawn material
2.2 Install sprinkler system
2.2.1 Identify sprinkler locations
2.2.2 Dig trencher
2.2.3 Install pipe and hardware
2.2.4 Cover sprinkler system
2.3 Plant grass
2.3.1 Remove debris
2.3.2 Prepare soil
2.3.3 Plant lawn seed
2.4 Plant shrubs
3.0 Build fence
3.1 Acquire fence material
3.2 Construct the fence
3.2.1 Mark fence line and posts
3.3.2 Install posts
3.3.3 Install fencing and gates
3.3.4 Paint/stain fence
Work packages
Summary tasks

## Slide 9: WBS (4/5)
Building a good WBS makes it easy for everyone on the project to understand his/her role and it makes managing the project much easier, too.
In this framework, Work Package size should follow:
8/80 hour rules
The reporting period rule time length between two status meetings/reporting points

## Slide 10: WBS (5/5)
Example 2: the ITER Work Breakdown Structure

## Slide 11: WBS Rules
Building a good WBS:
few rules to follow
Define activities
Sequence activities;
Estimate activities durations;
Estimate activities resource requirements;
Develop schedule

## Slide 12: Define activities (1/3)
It starts with the full details
It starts at the goal level
The 2 most common approaches

## Slide 13: Define activities (2/3)
Perform analysis
Define hardware requirements
Database
Activity name should include a strong verb and a strong noun
Why ?
To avoid Open Ended Activities

## Slide 14: Define activities (3/3)
Activity attribute extend the description of the activity
Few examples: activity code (ID), activity descriptions, predecessor activities, successor activities, logical relationships, resource requirements, imposed date, constraints, etc.

## Slide 15: WBS Rules
Building a good WBS:
few rules to follow
Define activities
Sequence activities;
Estimate activities durations;
Estimate activities resource requirements;
Develop schedule

## Slide 16: Sequence activities (1/3)
…to determinate the relationships among the project activities
Activity Network Diagram (AND)

## Slide 17: Sequence activities (2/3)
…to determinate the order in which this activities are performed
Gantt chart
First major applications of Gantt charts was during World War 1.

## Slide 18: Sequence activities (3/3)
The main 4 types of dependences
Finish-to-start (FS)
Finish-to-Finish (FF)
Start-to-Start (SS)
Start-to-Finish (SF)

## Slide 19: WBS Rules
Building a good WBS:
few rules to follow
Define activities
Sequence activities;
Estimate activities durations;
Estimate activities resource requirements;
Develop schedule

## Slide 20: Estimating activity duration
Main Methods to Estimating Activity Duration
Similarity to other estimations
Historical Data
Expert advice
Parametric estimation
3-Points Technique
It is a challenging  in particular for Scientific Project
This concept originates with the Program Evaluation and Review Technique (PERT). PERT uses 3 estimates to define an approximate range for each activity:
texpected =(toptimistic+4*tmost likely+tpessimistic)/6
[ Ref: D. G. Malcolm, J. H. Roseboom et C. E. Clark, Application of a technique for Research and Development Program Evaluation, Special Project Office, US Navy (1959)]

## Slide 21: WBS Rules
Building a good WBS:
few rules to follow
Define activities
Sequence activities;
Estimate activities durations;
Estimate activities resource requirements;
Develop schedule

## Slide 22: Estimate Activity Resource Requirements
By definition resources are required to complete each project activity (see Lecture 5) the Main Methods to Estimating Activity Duration could be also used to estimate Activity Resource Requirements.
5 Types of Resources
People
Facilities/Services
Equipments
Money
Materials

## Slide 23: WBS Rules
Building a good WBS:
few rules to follow
Define activities
Sequence activities;
Estimate activities durations;
Estimate activities resource requirements;
Develop schedule

## Slide 24: Develop schedule
Milestones
A significant point or event in the project
It is the process to analyzing activity sequences, duration, resource requirements and schedule constraints

## Slide 25: Milestone Schedule

## Slide 26: D.O.E. check point guidelines
Logical network properly created.
  Activities not linked < 5%
  F to S relations > 75%
  Avoid negative float
  Be aware of how leads and lags are used
Resource load all activities.
Estimate duration with 70% confidence level.
Break down activities to a level making it possible to take credit for progress made.

## Slide 27: The 3 method of analysis
Critical Path Method (CPM) or Program Evaluation and Review Technique (PERT)  activity-on-arrow diagram
Precedence Diagramming Method (PDM)  activity-on-node diagram
Linear Planning (LP)

## Slide 28: Activity-on-arrow vs. Activity-on-node

## Slide 29: Critical Path Method (1/4)
The Critical Path is the longest path or sequence of activities (in terms of activities duration) through the Network diagram
The Critical Path drives the completion date of the project.
It is the path with the longest duration time of the project!
[ Ref: J. E. Kelley, Critical-Path Planning and Scheduling: Mathematical Basis, Operation Research Article (1961)]

## Slide 30: Critical Path Method (2/4)
Critical Path in evidence in a Gantt diagram

## Slide 31: Critical Path Method (3/4)
Critical Path in evidence in a AND

## Slide 32: Critical Path Method (4/4)
Magnets, Vacuum,
Cryogenics
Assembly Integration
Buildings
& Civil Engineering
Commissioning & Operation

## Slide 33: PDM Method (1/3)
The Precedence Diagramming Method (PDM) is an activity-on-node diagram
[ Ref: B. Roy, Contribution de la theorie des graphes a l'etude des problems d'ordonnancement, SEMA (1960)]

## Slide 34: PDM Method (2/3)
It expand the information of the Activity-on-arrow Network Diagram!
The most common information shown are:
The activity name (ID)
The normal duration time (t)
The early start time (ES)
The early finish time (EF)
The late start time (LS)
The late finish time (LF)
The Free Float (FF) /The Total Float (TF)
ID | t
ES | EF
LS | LF
FF | TF
For each Project activity
The Float is the amount of time that an activity in a Project Network can be delayed without causing a delay to:
subsequent tasks (“Free Float")
project completion date (“Total Float") (i.e. the schedule flexibility)

## Slide 35: PDM Method (3/3)
Example 3: a PDM calculation
A1 | 5
0 | 5
0 | 5
0 | 0
A3 | 9
5 | 14
5 | 14
0 | 0
A2 | 7
0 | 7
4 | 11
4 | 4
A4 | 3
7 | 10
11 | 14
4 | 4
0
0
14
14
Activity name | Duration (day) | Start to Finish relationship
A1 | 5 | -
A2 | 7 | -
A3 | 9 | A1
A4 | 3 | A2
Project start node
Project end node
Earliest date
Earliest date
Latest date
Latest date
Project Data
The early start time (ES)
The early finish time (EF)
The late start time (LS)
The late finish time (LF)
The Free Float (FF) /The Total Float (TF)

## Slide 36: Linear Planning (1/3)
Many types of projects contain repeated blocks of activities across many work area.
“Fetta di Polenta”
Antonelli, Torino
Time

## Slide 37: Linear Planning (2/3)
Examples of these kinds of projects include road and high-rise construction.
Time

## Slide 38: Linear planning (3/3)
Example 4: CNGS schedule – CERN site
Time

## Slide 39: Project Schedule
The Project Schedule is the most recent version project status .
The Project Schedule is developed from the Schedule network analysis and used to benchmark the project status.

## Slide 40: Baseline schedule (1/3)
A Baseline Schedule is a specific version – accepted and approved - of the Project Schedule
It is used to benchmark the project status.

## Slide 41: Baseline schedule (2/3)
How to avoid the common sentence from activity responsible “99% the task is finish”?
Create a Deliverable Oriented Schedule
Any Project activity should be oriented to produce deliverables
Deliverable are important to measure progress!

## Slide 42: Baseline Schedule (3/3)
Magnets, Vacuum,
Cryogenics
Assembly Integration
Buildings
& Civil Engineering
Commissioning & Operation

## Slide 43: Project Management Plan
The Baseline Schedule is included in the Project Management Plan
See Lecture 2

## Slide 44: End – Lecture 4 Project Planning
Summary
WBS
Critical Path
Baseline Schedule