## Slide 1: 60 Years of Project Management at CERN
Pierre Bonnal

## Slide 2: Agenda
Today Facilities = Yesterday Projects!
PRAM in the Sixties
NSMPM in the Seventies
POL in the Eighties
Web-based tools of the Nineties
Project Control 2.0 in the years 2000s
IMPACT and openSE in the years 2010s
Will Project Planning & Scheduling 2.0 be next?

## Slide 3
Today Facilities = Yesterday Projects

## Slide 4
What?
Does CERN a secret society?

## Slide 5
It’s a detective
story about a
secret society
which…
… steals 1 g of antimatter
from a place called CERN…
… to blow up the Vatican …
Not a secret society!

## Slide 6: What means “CERN”? 1952
European
Council for
Nuclear
Research
Conseil Européen pour la Recherche Nucléaire
Third Session of the provisional
CERN Council in Amsterdam on 4 October 1952.
At this session, Geneva was chosen as the site
for the Laboratory and it was decided
to build a 25-30 GeV Proton Synchrotron.

## Slide 7: What means “CERN”? 1954
European Organization for Nuclear Research
Organisation Européenne pour la Recherche Nucléaire
European Laboratory for Particle Physics

## Slide 8: Member states and a few figures
12 member states in 1954
21 member states: Austria, Belgium, Bulgaria, the Czech Republic, Denmark, Finland, France, Germany, Greece, Israel, Italy, Hungary, the Netherlands, Norway, Poland, Portugal, Slovakia, Spain, Sweden, Switzerland, the United Kingdom
2 candidates for accession: Romania, Serbia
8 observers to CERN’s Council: India, Japan, the Russian Federation, the United States of America, Turkey, the European Commission, UNESCO
Applicants to become member states: Cyprus, Slovenia, Turkey or associate members: Brazil, Ukraine, India
ca. 2500 staff & ca. 900 other paid personnel ca. 12000 users from 600+ institutes & universities
ca. CHF 1.1 billion budget (2014)

## Slide 9
Why?
Why CERN exists?

## Slide 10
Where do we come from?
Where are we going to?

## Slide 11: Particle Physics’ Standard Model
Courtesy of ParticleZoo.net
matter
UP
DOWN
CHARM
STRANGE
TOP
BOTTOM
quarks
ELECTRON
ELECTRON NEUTRINO
MUON
MUON NEUTRINO
TAU
TAU NEUTRINO
leptons
gluons
photons
bosons
gravitons
forces
ORDINARY MATTER

## Slide 12
“Big Bang”

## Slide 13: Some questions to answer
What is mass? → Higgs boson
Matter is only 4% … dark matter and dark energy? → Supersymmetric particles
Matter – antimatter imbalance? → Symmetry breaking
Conditions in first second of Universe’s life? → Quark-gluon plasma
Do extra dimensions of space really exist? → String theory particles

## Slide 14: Why are we doing research in physics?
Galileo
James Maxwell

## Slide 15
How?
How does CERN answer these questions?

## Slide 16
+
=
truffles
a promising wood
a farmer
a pig
+
Theoreticians develop theories
Experimenters build experiments

## Slide 18
particle accelerators +
particle detectors
+
computing facilities

## Slide 20: The largest particle accelerators
  50 km+ of tunnels H+ and Pb82+
  More than 1600 superconducting cryomagnets
  Ultrahigh vacuum: 10-11 mbar (ultrahigh vacuum) i.e. 10 × emptier than on the Moon
  1.8 K ≈ –271°C that makes CERN the coldest place of the Universe!
  In safe conditions!
Courtesy of F. Briard

## Slide 21: A few figures…

## Slide 23: The biggest and most sophisticated particle detectors
  Cathedrals of science 100 m underground
  600 million collisions per second detected by hundreds of million sensors
  Thousands of collaborators for each detector
  In safe conditions!
Courtesy of F. Briard

## Slide 25: The most extensive scientific computing grid
  20 petabytes (20 millions of GB) of data every year
  100’000 processors
  200 computer centres around the world
Courtesy of F. Briard

## Slide 26
LHC Front-End Project launched in 1984
LHC Project approved in 1994
First circulating beams in 2008
Final Project Cost = CHF 6+ billion

## Slide 27
So what?
(spin-offs)

## Slide 28: Practical applications: the World Wide Web
  It was developed in the frame of the LHC project in 1989!
  Freely given to the World!
Courtesy of F. Briard

## Slide 29: Practical applications: cancer treatment
  For both detection and cure of cancers
  PET Scans
  Hadron Therapy
Courtesy of F. Briard

## Slide 30: Practical applications: customs checks
  Scanning trucks in less than one hour without unloading them!
Courtesy of F. Briard

## Slide 31: Practical applications: using the grid
  Ultra high-speed processing of satellite imagery in the case of natural disasters
Courtesy of F. Briard

## Slide 32
  September 10th 2008: First beams circulating in the LHC (2 bunches)
  September 19th 2008: development of resistive zone in dipole bus bar slice, then electrical arc that punctured the helium enclosure
  18-month repair
  March 30th 2010: Beams back in the LHC (3.5 TeV + 3.5 TeV)
  July 4th 2012: “CERN experiments observe particle consistent with long-sought Higgs boson”
  2013 Nobel Prize

## Slide 33
60 years of CERN vs. centuries of PM

## Slide 34: The advent of project management
Ancient Egypt
Brunelleschi
Smeaton
Gantt
Adamiecki
1959

## Slide 35: The advent of project management
new product
training / HR
events
PROJECTS
computing
construction
industrial plant
organizational
new service

## Slide 36: First PM issue
With large-scale projects, one shall not impose a PM methodology!

## Slide 37: The advent of project management
Project Integration Management
Project Scope Management
Project Time Management
Project Cost Management
Project Quality Management
Project Human Resource Management
Project Communications Management
Project Risk Management
Project Procurement Management
Project Stakeholders Management

## Slide 38
PRAM in the Sixties

## Slide 39: PRAM in the Sixties
CERN PS 56-59
CPM in 1959
PERT in 1959
PDM in 1960-68
PRAM in 1966
RCPS in mid-60s
CERN ISR 67-71

## Slide 40: PRAM in the Sixties

## Slide 41: The Seventies
CERN SPS 71-76
Many thanks to Ph. Lebrun

## Slide 42
POL in the Eighties

## Slide 43: POL in the Eighties
CERN LEP 83-89
Many thanks to Ph. Lebrun

## Slide 44
Web-based tools of the Nineties

## Slide 45: Web-based tools of the Nineties

## Slide 46
PPT-EVM and Project Control 2.0 in the years 2000s

## Slide 47: Second PM issue
Large Hadron Collider 1995-2008
Multi-billion-CHF project  very large scale Many contributors, several sources of funding
Highly technological project  several challenges Sufficient room for creativity and innovation
Performance-driven project  it must work! Even if it takes more time and more resources
Highly distributed project  really worldwide!
Public-funded project  public auditors

## Slide 48: Second PM issue (cont’d)
In 1994  “Must Win” project, under-funded and under-resourced!
All CERN’s departments involved in some ways
LHC Project Leader appointed as a director
Budgeting and cost control  Project Administrator
Planning and scheduling  Technical Co-ordinator
No link between the cost control system (cost packages) and the scheduling system (work packages)

## Slide 49: Second PM issue (cont’d)
Technical Co-ord.  “the project is behind schedule”
Project Administrator  “the project is under-running”
The LHC Project Management Team was not in capacity to demonstrate that EAC < TAB
Member States asked CERN Management to set up an appropriate Project Control System

## Slide 50: Project Control 2.0
Multi-level planning and scheduling 3 levels  master, co-ordination and detailed
Earned Value Management-based
Interfaced to accounting system  Actual Costs
Interfaced to contract management system
Interfaced to human resource management system
In-kind contributions
Collaborative and web-based  obvious!
Lean  planning + reporting by Project Engineers
Notes: • Multi-level planning and scheduling, 3 levels  master, co-ordination and detailed
• Earned Value Management-based
Interfaced to CERN’s accounting systems, to get accurate information on actual costs
Interfaced to CERN’s contract management system, to ease the management of the contracts and protocols
Interfaced to CERN’s human resource system
That manages in-kind contributions
That is web-based

## Slide 51: Project Control 2.0 (cont’d)
But how to get rid of the 90%-syndrome?
Activity
completed?
Progress still 95%!
Activity
completed?
Progress 90%!
An activity of the project
Activity
not started
Progress 0%
Activity
half-way
Progress 50%
Activity
almost done
Progress 90%
Deliverable-oriented PM System
Notes: • Multi-level planning and scheduling, 3 levels  master, co-ordination and detailed
• Earned Value Management-based
Interfaced to CERN’s accounting systems, to get accurate information on actual costs
Interfaced to CERN’s contract management system, to ease the management of the contracts and protocols
Interfaced to CERN’s human resource system
That manages in-kind contributions
That is web-based

## Slide 52: Project Control 2.0 (cont’d)
Transparency of the physical progress reporting A “10 magnets out of 20” physical progress statement is more informative than a “50% complete” statement!
Payment milestones of result-oriented contracts refer to effective deliveries Finish dates of contract activities are always known!
Finally, a trend in project management practices (ref. Patrick A. Howard. Deliverable-oriented project management. ProjectWorld’98 Proceedings, 1998)

## Slide 53: Project Control 2.0 (cont’d)

## Slide 54: Project Control 2.0 (cont’d)
4 types of activities

## Slide 55: LHC Project EVMS | Weak points
Introduced while AC = CHF 1 billion!!
Granularity between contract breakdown structure, co-ordination schedule, codes of accounts…
Too many activities  12’000+ activities
Varying granularity of activities: from a few kCHF to several MCHF from a few weeks to several months
Project Engineers planned too optimistically
Weak integration with schedule networks

## Slide 56: LHC Project EVMS | Lessons learned
No. of planned activities < 500 Work Package vs. Planned Package features
Constrain the size of the activities so that:
  80% of the activities in range 0.2% – 2% BAC
  Duration < 10% project duration and 3 months
  No. of level-of-effort activities in range 1 – 1%
  Unambiguous responsibility  only one per activity
Systematics in breaking down to ease taking over

## Slide 57: LHC Project EVMS | Strong points
Deliverable-orientation  collaborative framework
Strong Project Leader support  essential!
Microsoft® Excel® sheets to interact with DBs
Strongly integrated with corporate databases
Planned (baseline) vs. expected (trend) figures
“AC = EV rule” for in-kind contributions
One repository of activities for all groups (eliminate overlap, detect holes…)
Contributed to cost consciousness at all levels
Regain confidence of CERN’s Member States

## Slide 58: Improvements
Embed a resource-constrained critical path engine
Embed repetitive & linear scheduling methods functionalities
Manage better the Project Management Reserve in synchronization with change records

## Slide 59: Repetitive scheduling

## Slide 60: 3 levels of planning & scheduling

## Slide 61
IMPACT, planbook and openSE in the years 2010s

## Slide 62: IMPACT & planbook in the years 2010s

## Slide 63: openSE in the years 2010s
GSI FAIR (Germany)
CERN (Switzerland)
TUT (Finland)
UPM (Spain)
KIT (Germany)
Sensetrix (Finland)
bgator (Finland)
Oxford Technology (UK)
The research leading to this framework has received funding from the European Commission under the FP7 ITN project PURESAFE, grant agreement no. 264336.
A&M ParisTech (France)
U. de Savoie (France)
= 15 early-stage researchers
ESS (Sweden)
F4E (Spain) ?

## Slide 64: openSE in the years 2010s
The need:
A systems engineering (SE) framework suited to scientific facilities and systems that are subject to ionizing radiations
The preferred solution:
Participative-based every project/systems engineer contributes actively to managerial tasks
Lean thinking-based enhance outcome value while limiting waste
Open source-based creative common license

## Slide 65: openSE in the years 2010s
framework
80-page booklet
guidelines
4-page flyers
project management
systems engineering
remote engineering

## Slide 66: openSE in the years 2010s

## Slide 67: openSE in the years 2010s

## Slide 68: openSE

## Slide 69
Will Project Planning & Scheduling 2.0 be next?

## Slide 70: Planning & Scheduling 2.0

## Slide 71: CPM Algorithm

## Slide 72: PDM Algorithm

## Slide 73: Planning & Scheduling 2.0

## Slide 74: Planning & Scheduling 2.0

## Slide 75: Planning & Scheduling 2.0

## Slide 76: Planning & Scheduling 2.0
Mathieu Baudin’s PhD thesis (A&M ParisTech)
Algorithms developed and prototype working
Algorithms under tests at GSI Darmstadt
Algorithms principles  article in JMPM
Algorithms  DSM Conference, July 2014, Paris
Will they be embedded in IMPACT?
Will they be embedded in commercial packages?

## Slide 77
CERN has always been on the cutting edge in matter of particle physics
CERN has always been on the cutting edge in matter of technologies
CERN has also always been on the cutting edge in matter of project management